## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | ORD/000425/2021-2022 | 2033/BHM | 09/12/2021 | 07/02/2022 | TAPAN KUMAR DATTA | 94.18 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-5) | AE | JE | ORD/000005/2021-2022 | 1019/BHM | 17/06/2021 | 16/08/2021 | SUNIL RABI DAS | 50.07 | 49.78 | 99.42 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat - II Block under Brbhum Division, PHE Dte. (Sl. No.04) | AE | JE | ORD/000331/2020-2021 | 36 / BH | 26/02/2021 | 18/03/2021 | BIJOY KUMAR CHOWDHURY | 4.84 | 4.84 | 99.88 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000366/2021-2022 | 179/BH | 03/11/2021 | 18/11/2021 | BIJOY KUMAR CHOUDHURY | 3.73 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | ORD/000664/2021-2022 | 2033/ BHM | 09/12/2021 | 07/02/2022 | TAPAN KUMAR DATTA | 94.18 | 0 | 0 | 40
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Sashtitalapara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000367/2021-2022 | 178/BH | 03/11/2021 | 18/11/2021 | M/S K.S. GHOSH | 3.64 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000370/2021-2022 | 180/BH | 03/11/2021 | 18/11/2021 | MUKADDUMUL MOULA | 3.86 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000364/2021-2022 | 177/BH | 03/11/2021 | 18/11/2021 | TAPAN ENTERPRISE | 4.83 | 0 | 0 | 50
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Konaipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000162/2020-2021 | 34/BH | 26/02/2021 | 18/03/2021 | MUKADDUMUL MOULA | 4.84 | 4.84 | 99.87 | 0
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Sashtitalapara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000165/2020-2021 | 37/BH | 26/02/2021 | 18/03/2021 | M/S K.S. GHOSH | 4.84 | 4.84 | 99.92 | 0
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000163/2020-2021 | 35/BH | 26/02/2021 | 18/03/2021 | M/S S.N CONSTRUCTION | 4.84 | 4.84 | 99.88 | 0
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum | SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Baroipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000166/2020-2021 | 38/BH | 26/02/2021 | 18/03/2021 | TAPAN ENTERPRISE | 4.84 | 4.84 | 99.88 | 0
Total | [13 empty] | 278.72 | 73.97 | 26.54