## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Post Office Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 05) | AE | JE1 | ORD/000457/2021-2022 | 07/BSSD | 17/01/2022 | 06/02/2022 | PRANAB KUMAR MONDAL | 4.56 | 4.39 | 96.3 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE |  | ORD/000456/2021-2022 | 06/BSSD | 17/01/2022 | 06/02/2022 | INDRANIL DUTTA | 4.56 | 4.29 | 93.94 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.6) | AE | JE2 | ORD/000341/2021-2022 | 1773/BHM | 28/10/2021 | 27/12/2021 | M/S GOUTAM DAS | 79.89 | 69.39 | 86.85 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-V under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte.¿(Sl. No.3) | AE | JE1 | ORD/000342/2021-2022 | 1772/BHM | 29/10/2021 | 28/12/2021 | PRANAB KUMAR GHOSH | 79.83 | 79.2 | 99.2 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.4) | AE | JE2 | ORD/000352/2021-2022 | 1820/BHM | 03/11/2021 | 02/01/2022 | MD. HASIN | 79.86 | 72.91 | 91.29 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub=Division within Birbhum Division, P.H.E. Dte. (Sl. No. 2) | AE | JE1 | ORD/000357/2021-2022 | 1851/BHM | 09/11/2021 | 08/01/2022 | SAKTI ENTERPRISE | 79.88 | 79.55 | 99.59 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.5) | AE | JE2 | ORD/000343/2021-2022 | 1774/BHM | 29/10/2021 | 28/12/2021 | M/S KRIPASINDHU GHOSH & CO. | 79.85 | 79.64 | 99.74 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Deshalpur, Gopalpur, Maliha, Ekdala, Haripur, Khosnatore, Jamal, Fathepur and Kubirpur (Zone-IV) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.6) | AE | JE1 | ORD/000276/2022-2023 | 2218/BHM | 13/10/2022 | 12/12/2022 | THREE MAA ENTERPRISE | 51.45 | 51.44 | 99.98 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE3 | ORD/000043/2022-2023 | 1062/BHM | 13/05/2022 | 12/07/2022 | APURBA MONDAL | 59.53 | 56.42 | 94.79 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone III under Suri-I, Suri II & Sainthia Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.11) | AE | JE1 | ORD/000427/2021-2022 | 2170/BHM | 28/12/2021 | 26/02/2022 | M/S BUILDWELL | 79.48 | 76.19 | 95.86 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Goala Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 03) | AE | JE1 | ORD/000461/2021-2022 | 05/BSSD | 17/01/2022 | 06/02/2022 | PUSPAJIT MONDAL | 4.58 | 4.12 | 90.03 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Sainthia Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | AE | JE | ORD/000432/2021-2022 | 400/BSSD | 14/12/2021 | 03/01/2022 | SUBHRADIP SARKAR | 0.99 | 0 | 0 | 50
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | AE | JE3 | ORD/000406/2021-2022 | 380/BSSD | 10/12/2021 | 30/12/2021 | AATHARVA CONSTRUCTION | 0.99 | 0.8 | 80.07 | 50
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Co-Operative Coloney at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE1 | ORD/000602/2021-2022 | 322/BSSD. | 13/09/2021 | 03/10/2021 | RANJIT GHOSH | 4.09 | 2.89 | 70.68 | 100
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Construction of Operator Cum Switch Room 5.00mtr. X 4.00mtr.Size at Zone-IV for the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte (Sl. No.04) | AE | JE3 | ORD/000862/2021-2022 | 1083/BHM | 02/07/2021 | 15/09/2021 | PRANAB KUMAR MONDAL | 4.96 | 0 | 0 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) | AE | JE1 | ORD/000601/2021-2022 | 319/BSSD.. | 13/09/2021 | 03/10/2021 | ARPAN PANDIT | 4.09 | 3.63 | 88.8 | 100
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Dutta Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 02) | AE | JE1 | ORD/000517/2021-2022 | 320/BSSD. | 13/09/2021 | 03/10/2021 | DIPAK SARKAR | 4.09 | 3.67 | 89.76 | 100
18 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-I under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE | JE3 | ORD/000061/2022-2023 | 1063/BHM | 13/05/2022 | 12/07/2022 | SYED KHORSID ALAM | 59.55 | 59.45 | 99.82 | 72
19 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE3 | ORD/000352/2022-2023 | 2654/BHM | 01/12/2022 | 15/01/2023 | APURBA MONDAL | 17.61 | 17.55 | 99.64 | 100
20 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Piped Water Supply Scheme within Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000039/2023-2024 | 1160/BHM | 11/04/2023 | 26/05/2023 | MD. HASIN | 12.73 | 12.67 | 99.51 | 100
21 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV & V under Suri-I, Suri-II & Sainthia W/S Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000052/2023-2024 | 1259/BHM | 17/04/2023 | 01/06/2023 | PRANAB KUMAR GHOSH | 24.87 | 24.86 | 99.97 | 100
22 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II and Sainthia Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000605/2022-2023 | 1049/BHM | 31/03/2023 | 15/05/2023 | M/S GOUTAM DAS | 29.73 | 29.7 | 99.91 | 100
23 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000091/2023-2024 | 1642/BHM | 02/05/2023 | 16/06/2023 | S R ENTERPRISE | 8.37 | 2.15 | 25.73 | 100
24 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-III under Suri-I, Suri-II & Sainthia W/S Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000088/2023-2024 | 1634/BHM | 02/05/2023 | 16/06/2023 | M/S BUILDWELL | 19 | 17.02 | 89.6 | 100
25 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000094/2023-2024 | 1641/BHM | 02/05/2023 | 16/06/2023 | SAKTI ENTERPRISE | 7.04 | 3.48 | 49.46 | 100
26 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000599/2022-2023 | 1044/BHM | 31/03/2023 | 15/05/2023 | ARKA JYOTI GHOSH | 20.49 | 20.42 | 99.67 | 100
27 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000350/2022-2023 | 2652/BHM | 01/12/2022 | 15/01/2023 | AVIJIT CHANDA | 17.72 | 16.49 | 93.07 | 0
28 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE |  | ORD/000644/2022-2023 | 298/BSSD | 15/12/2022 | 04/01/2023 | NEEL ENTERPRISE | 1 | 0.99 | 99.37 | 0
29 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area for Swajal Gram at Nutandanga, Bhromorekole, Patanda, Bedaipur & Bhagabanbati of Zone-V under Suri-I, Suri-II & Sainthia W/S Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (2nd Call) | AE | JE1,JE2 | ORD/000677/2023-2024 | 1037/BHM | 15/03/2024 | 29/04/2024 | M/S C.P. CONCERN | 2.12 | 0 | 0 | 0
30 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Balance FHTC for the villages of Karimpur & rest portion of Dhalla, Kunuri & all other allied works for Zone-II of Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II & Sainthia Block within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000692/2023-2024 | 1039/BHM | 15/03/2024 | 14/04/2024 | PRONAB KUMAR DEY | 11.79 | 0 | 0 | 0
31 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block | SM/08286 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | AE | JE | ORD/000695/2023-2024 | 1043/BHM | 15/03/2024 | 29/04/2024 | ANIRUDDHA FARUQUE | 20.12 | 0 | 0 | 0
Total | [13 empty] | 874.82 | 793.31 | 90.68