## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Construction of Switch Room Cum Chlorine Room 3.60 mtr. x 3.00 mtr. Size at 2nd Tube well site of CHAUHATTA Piped Water Supply Scheme at Labpur Block under Bolpur Sub-Division , P.H.E Dte. within Birbhum Division P.H.E. Dte. (Pump House No. - 2). (Sl. No.: 8) | AE | JE1 | ORD/000810/2021-2022 | 328/BSD | 01/09/2021 | 31/10/2021 | NAZIR HOSSAIN | 4.09 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | AE | JE1 | ORD/000654/2021-2022 | 37/BSD | 02/02/2022 | 17/02/2022 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Construction of Switch Room Cum Chlorine Room 3.60mtr. x 3.00mtr. Size under Piped Water Supply Scheme for CHAUHATTA Water Supply Scheme at Labpur Block under Bolpur Sub-Division, P.H.E Deptt. within Birbhum Division P.H.E. Deptt.. ( Pump House No.- III). (Sl. No.: 02). | AE | JE1 | ORD/000085/2022-2023 | 256/BSD | 07/07/2022 | 05/09/2022 | NAZIR HOSSAIN | 4.05 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Repairing of existing road and construction of new approach road towards O.H.R. in front of Head Works site of Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03) | AE | JE1 | ORD/000583/2021-2022 | 458/BSD | 13/12/2021 | 12/01/2022 | NAZIR HOSSAIN | 1.94 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Laying of Distribution Pipeline with FHTC work at Chowhatta village of Chowhatta Water Supply Scheme due to CMRO Grievance (Grievance Lodging Date: 15.12.2023, Complainant Name: Sk Indadul) in Chowhatta Mohodori - I Gram Panchayet under Bolpur Sub-Division within Birbhum Division, PHE. Dte | AE | JE1 | ORD/000618/2023-2024 | 166/BSD | 15/02/2024 | 22/02/2024 | SK.RUHUL AMIN | 0.96 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08891 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Chowhata Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000155/2022-2023 | 1850/BHM | 30/08/2022 | 29/10/2022 | JDJ ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 99.46 | 0 | 0 | 80
Total | [13 empty] | 111.17 | 0 | 0