## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area at Dakshin Tilpara Nutanpara, Sukantapally & Mudidangal of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. ¿ 04) | AE | JE3 | ORD/000046/2022-2023 | 90/BSSD | 27/05/2022 | 16/06/2022 | RAJKUMAR DAS | 4.95 | 4.58 | 92.52 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. -09) | AE | JE3 | ORD/000143/2022-2023 | 167/BSSD | 16/08/2022 | 05/09/2022 | SACHIN KUMAR SARKAR | 2.72 | 2.3 | 84.74 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. -08) | AE | JE3 | ORD/000288/2022-2023 | 262/BSSD | 20/10/2022 | 09/11/2022 | M/S SARADA CONSTRUCTION. | 2.67 | 2.1 | 78.41 | 91
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) | AE | JE1 | ORD/000600/2021-2022 | 319/BSSD. | 13/09/2021 | 03/10/2021 | ARPAN PANDIT | 4.09 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from OHR towards Kalitala (Tilpara) under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 19) | AE | JE3 | ORD/000157/2021-2022 | 274/BSSD | 06/08/2021 | 26/08/2021 | PUSPAJIT MONDAL | 4.94 | 4.91 | 99.32 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) | AE | JE3 | ORD/000275/2021-2022 | 336/BSSD | 23/09/2021 | 13/10/2021 | M/S SARADA CONSTRUCTION. | 4.02 | 4.01 | 99.8 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | AE | JE3 | ORD/000406/2021-2022 | 380/BSSD | 10/12/2021 | 30/12/2021 | AATHARVA CONSTRUCTION | 0.99 | 0 | 0 | 50
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | AE | JE3 | ORD/000553/2021-2022 | 353/BSSD. | 25/10/2021 | 14/11/2021 | SACHIN KUMAR SARKAR | 3.88 | 3.88 | 99.78 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) | AE | JE3 | ORD/000257/2021-2022 | 1506/BHM | 09/09/2021 | 08/11/2021 | RAJKUMAR DAS | 39.43 | 39.29 | 99.63 | 50
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from Kalitala(Tilpara) towards PWD (Roads) office under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 02) | AE | JE3 | ORD/000156/2021-2022 | 273/BSSD | 06/08/2021 | 26/08/2021 | UTPAL DEY | 4.92 | 4.91 | 99.92 | 0
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Trial Bore and Sinking of 200 mm dia. replacement tubewell 3 (Three) nos. each 39 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi including connecting pipe line under Tilpara Piped Water Supply Scheme within Birbhum Division, PHE Dte. | AE | JE,JE3 | ORD/000144/2024-2025 | 2506/BHM | 03/09/2024 | 18/10/2024 | AMIT KUMAR ROY | 7.63 | 6.26 | 82 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Laying of UPVC Pipeline including all allied works for By passs arrangement at Kamalpur village for smooth supply of drinking water through existing FHTC under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. | AE | JE,JE2,JE3 | ORD/000493/2024-2025 | 205/BHM | 16/01/2025 | 02/03/2025 | RAJ KUMAR DAS | 1.29 | 0 | 0 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. | SM/08892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Laldighipara under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | AE | Estimator | ORD/000611/2023-2024 | 909/BHM | 13/03/2024 | 27/04/2024 | RAJKUMAR DAS | 2.89 | 0 | 0 | 100
Total | [13 empty] | 84.43 | 72.23 | 85.55