## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | Retrofitting | Trial Run of pipeline (CI/ DI/ UPVC) (Distribution Main & Rising Main ), Sluice Valve/ Air Valve/ Non Return Valve, S.S.P. etc. of INDAS Water Supply Scheme , under Bolpur Sub-Division within Birbhum Division, P.H.E. Dte. (from 01.05.2022 to 31.07.2022). (Sl. No.: 03). | AE | JE1 | ORD/000056/2022-2023 | 173/BSD | 29/04/2022 | 30/07/2022 | QUAZI SIRAJUL ISLAM. | 1.13 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | Retrofitting | Rising Main Pipe line from TW1, TW2 to OHR including of CI specials for proposed INDUS piped Water Supply Scheme, under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.: 1) | AE | JE1 | ORD/000596/2020-2021 | 21/BSD | 29/01/2021 | 28/02/2021 | SYED HASMAT ALI | 1.45 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | Retrofitting | Supply and delivery of 80mm dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Indas Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03). | AE | JE1 | ORD/000657/2021-2022 | 27/BSD | 21/01/2022 | 05/02/2022 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08895 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of "INDUS W/S Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. " (Sl. No. 05) | AE | JE1 | ORD/000414/2021-2022 | 2065/BHM | 13/12/2021 | 11/02/2022 | QUAZI SIRAJUL ISLAM. | 61.02 | 42.31 | 69.34 | 100
Total | [13 empty] | 64.26 | 42.31 | 65.85