## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | Retrofitting | Laying, Fitting, Fixing and jointing of Rising Main from 1st & 2nd Tube-well to O.H.R of D.I. (K-9) pipe at Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 02) | AE | JE4 | ORD/000701/2021-2022 | 242/BSD | 16/07/2021 | 15/08/2021 | SYED HASMAT ALI | 2.71 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | Retrofitting | ¿Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bipratikuri w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.4) | AE | JE4 | ORD/000305/2021-2022 | 1693/BHM | 07/10/2021 | 06/12/2021 | M/S KRIPASINDHU GHOSH & CO. | 72.44 | 71.71 | 98.99 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | Retrofitting | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 02). | AE | JE2,Bolpur Sub-Division | ORD/000658/2021-2022 | 36/BSD | 02/02/2022 | 17/02/2022 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. | SM/08897 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Lalbazar, Malitpur, Saripa and Talbana within the Command area of Bipratikuri Water Supply Scheme (Phase-I) for Swajal Gram under Labpur Block of Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.5) | AE | JE3 | ORD/000491/2022-2023 | 288/BHM | 01/02/2023 | 18/03/2023 | M/S KRIPASINDHU GHOSH & CO. | 21.33 | 19.3 | 90.49 | 100
Total | [13 empty] | 97.13 | 91.01 | 93.7