## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tarapit Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE1,JE2 | ORD/000336/2021-2022 | 1770/BHM | 29/10/2021 | 28/12/2021 | SUNIL RABI DAS | 80.28 | 75.81 | 94.42 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Karkaria mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-23) | AE | JE1,JE2 | ORD/000182/2022-2023 | 278/RSD | 18/08/2022 | 17/09/2022 | SHIB GANGA CONSTRUCTION | 4.99 | 4.99 | 100 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Tarapur mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-24) | AE | JE1,JE2 | ORD/000184/2022-2023 | 280/RSD | 22/08/2022 | 21/09/2022 | SHIB GANGA CONSTRUCTION | 4.98 | 4.98 | 100 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | Retrofitting | Laying of Distribution Main pipeline through crossing of PWD road at Karkaria more East side by adopting Jack Pushing method for Improvement of Tarapith PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000510/2021-2022 | 08/RSD | 04/01/2022 | 19/01/2022 | SUNIL RABI DAS | 4.14 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. | SM/08898 | Retrofitting | Laying, joining and interconnecting the tubewells (5 nos.) to OHR with HDPE pipes and Specials including Bypass arrangement for Improvement of Tarapith piped W/S Scheme under Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE1,JE2,JE3 | ORD/000709/2021-2022 | 1333/BHM | 18/08/2021 | 02/10/2021 | SACHIN KUMAR SARKAR | 16.23 | 0 | 0 | 100
Total | [13 empty] | 110.62 | 85.77 | 77.54