## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Construction of 300 Cum capacity and 20.0m staging height RCC Over Head Reservoir & Laying distribution system including all allied works as per departmental drawing (DRG. No. PC-I/OHR/07/2012) at Zone-V under the Piped Water Supply Scheme for Bandirban (Kanmara) Suri-I & Rajnagar Block under Birbhum Division, PHE Dte (Sl. No.5) | AE | JE2 | ORD/000714/2021-2022 | 1994/BHM | 07/12/2021 | 04/12/2024 | APURBA MONDAL | 180.84 | 0 | 0 | 87
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Kuralmita, Muktipur under Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No. - 02) |  |  | ORD/000268/2022-2023 | 000079 | 28/09/2022 | 28/10/2022 | ROY BISWAS CONSTRUCTION | 0 | 0 | NAN | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-VI Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte | AE | JE1,JE2 | ORD/000169/2024-2025 | 2709/BHM | 24/09/2024 | 14/09/2026 | BISWARUP GHOSH | 95 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Junedpur in Suri I, II & Sainthia covered under Bhandirbon Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000653/2023-2024 | 1023/BHM | 15/03/2024 | 14/05/2024 | ARKA JYOTI GHOSH | 31.99 | 6.47 | 20.22 | 25
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Itagoria in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar-Sub Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000656/2023-2024 | 1021/BHM | 15/03/2024 | 14/05/2024 | RANJIT GHOSH | 29.38 | 6.54 | 22.24 | 40
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-III Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2 | ORD/000666/2023-2024 | 1029/BHM | 15/03/2024 | 01/11/2026 | BIJOY KUMAR CHOUDHURY | 58.14 | 0 | 0 | 35
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-I Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE,JE2 | ORD/000650/2023-2024 | 1024/BHM | 15/03/2024 | 01/09/2026 | SACHIN KUMAR SARKAR | 58.53 | 9.89 | 16.89 | 75
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-V Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE,JE2 | ORD/000676/2023-2024 | 1038/BHM | 15/03/2024 | 15/07/2025 | SOUMEN CHATTERJEE | 48.94 | 2.68 | 5.47 | 35
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Choto Alaunda in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000652/2023-2024 | 1025/BHM | 15/03/2024 | 16/07/2024 | BHABANI ENTERPRISE | 30.93 | 6.36 | 20.56 | 35
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Bandirban Water Supply Water Supply Scheme within Birbhum Division, PHE Dte | AE | JE | ORD/000576/2023-2024 | 729/BHM | 28/02/2024 | 23/02/2025 | S R ENTERPRISE | 83.89 | 75.56 | 90.06 | 95
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-II Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000626/2023-2024 | 1013/BHM | 15/03/2024 | 14/01/2026 | BROTHERS ENTERPIRSE | 39.8 | 0 | 0 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Laying of distribution system including FHTC at Bandirban (Kanmara) Zone I, II, III Tasarkata, Ranpur & Lambodarpur Zone IV, Zone- V, VI Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | AE | JE | ORD/000619/2024-2025 | 611/BHM | 03/03/2025 | 01/06/2025 | SYED KHORSED ALAM | 183.69 | 0 | 0 | 0
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. | SM/09341 | Retrofitting | Laying of distribution system including FHTC at Karidhya, Kalipur, Amaipur, Laksmindarpur, Baramahula Chhora & Brojergram Mouza for Bandirban (Kanmara) Zone IV Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | AE | JE | ORD/000572/2024-2025 | 431/BHM | 10/02/2025 | 01/09/2025 | PREMANANDA ROY BISWAS | 189.3 | 0 | 0 | 75
Total | [13 empty] | 1030.45 | 107.49 | 10.43