## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Laying of Rising Main from Tube Well - I & Tube Well - II to O.H.R. for Tilutia Zone - II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000644/2021-2022 | 87/BSD | 10/03/2022 | 30/03/2022 | SYED HASMAT ALI | 2.65 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone -I Head work site of Tilutia water supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. 04) | AE | JE4 | ORD/000741/2021-2022 | 12/BSD | 11/01/2022 | 12/03/2022 | SANTU SEKH | 4.84 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Laying of Rising Main pipeline from Tube-well No. - I & II to O.H.R at Mahanpur of Tilutia Zone - I Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 15). | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000645/2021-2022 | 86/BSD | 10/03/2022 | 25/03/2022 | INDRAJIT DAS | 2.52 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone - II Head Works site of Tilutia Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. - 02) | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000825/2021-2022 | 17/BSD | 11/01/2022 | 12/03/2022 | MD SAFIUL HASSAN | 4.82 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Sinking of 02(Two) nos. 300mm X 200mm dia. X 300m deep Tube Wells by Rotary Rig for Tilutia-II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division, P.H.E Dte.(2nd Call) (Sl. No.5) | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000670/2020-2021 | 1503/BHM | 26/11/2020 | 25/01/2021 | PASCON | 32.45 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Supply and delivery of 300mm dia., 3.0 Mtr. long UPVC slotted pipe (Strainer) (CD) for sinking of 02 nos deep Tube-wells of Tilutia Zone - II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No.: 01). | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000840/2021-2022 | 479/BSD | 27/12/2021 | 11/01/2022 | PASCON | 2.05 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Adopting Jack Pushing of Hume Pipe (NP3/ NP4) as Cashing to Cross Water carrier Pipe in front of OHR at TILUTIA ZONE - II Water Supply Scheme under Bolpur Sub-Division, P.H.E. Deptt. (Sl. No.: 10). | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000110/2022-2023 | 242/BSD | 22/06/2022 | 12/07/2022 | S. S. CONSTRUCTION | 3.1 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Supply and delivery of 150mm and 100mm. dia. Sluice Valves including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Tilutia Zone - I & II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 02). | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000854/2021-2022 | 93/BSD | 11/03/2022 | 26/03/2022 | MAKALI ENGINEERING CORPORATION | 1.81 | 0 | 0 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of "Tilutia Zone - II under Tilutia Zone - II Water Supply Scheme within Birbhum Division PHE Dte." (Sl. No. - 8) | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000096/2022-2023 | 1476/BHM | 12/07/2022 | 10/09/2022 | RAJKUMAR DAS | 66.75 | 66.67 | 99.87 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilutia Zone-I under Tilutia Zone-I Water Supply Scheme within Birbhum Division, PHE Dte. | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000277/2022-2023 | 2245/BHM | 17/10/2022 | 16/12/2022 | MANAS KUMAR MONDAL | 66.75 | 66.74 | 99.99 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Balance FHTC works at different Villages within coverage area of Tilutia Water Supply Scheme (Zone-II) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.10) | AE | JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000534/2022-2023 | 665/BHM | 28/02/2023 | 13/07/2023 | INDRAJIT DAS | 25.54 | 15.21 | 59.55 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Dismantling & Restoration of cement concrete road for laying of distribution pipeline of Tilutia Zone - I Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01) | AE | JE2,Bolpur Sub-Division,JE4 | ORD/000688/2021-2022 | 446/BSD | 10/12/2021 | 09/01/2022 | M/S KRIPASINDHU GHOSH & CO. | 4.82 | 2.31 | 48.01 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. | SM/09362 | Retrofitting | Withdrawing of existing pipe for previous Head Work Site and relaying of 250mm. dia. DI pipes From OHR to Node point 192A due to Change of Head Work Site at Tilutia Zone - I Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 07). | AE,Assistant Engineer | JE2 ,JE2,Bolpur Sub-Division,JE4 | ORD/000059/2022-2023 | 204/BSD | 23/05/2022 | 01/12/2022 | ARABINDA GHOSH | 3.65 | 0 | 0 | 100
Total | [13 empty] | 221.75 | 150.93 | 68.06