## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09363 | Retrofitting | Sinking of 01 Nos (3 rd ) Tubewell 200mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Sekhpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000676/2021-2022 | 106/RSD | 07/03/2022 | 06/04/2022 | ISLAM CONSTRUCTION | 4.98 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09363 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sekhpur under Sekhpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.6) | AE | JE1 | ORD/000123/2022-2023 | 1611/BHM | 28/07/2022 | 26/09/2022 | M/S KRIPASINDHU GHOSH & CO. | 95.28 | 59.52 | 62.47 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09363 | Retrofitting | Rising main with DI pipe line for SHEKPUR Piped Water Supply Scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE,JE1,JE2,JE3 | ORD/000035/2022-2023 | 183/RSD | 02/05/2022 | 01/06/2022 | AJIMUL ISLAM | 3.98 | 0 | 0 | 100
Total | [13 empty] | 104.25 | 59.52 | 57.1