## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dantura under Dantura Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.5) | AE | JE2 | ORD/000209/2022-2023 | 2005/BHM | 15/09/2022 | 14/11/2022 | PRAVAT SARKAR | 95.17 | 93.87 | 98.63 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | Retrofitting | Construction of Pump House of 5.40mtr. X 3.6mtr. Size with sanitary and water supply arrangements at DANTURA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000663/2021-2022 | 16/AE/NSD | 17/01/2022 | 18/03/2022 | SHIB GANGA CONSTRUCTION | 4.99 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | Retrofitting | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Dantura Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000651/2021-2022 | 130/AE/NSD | 09/03/2022 | 08/04/2022 | SUNIL RABI DAS | 4.8 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09364 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Dantura Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000589/2022-2023 | 1014/BHM | 30/03/2023 | 29/05/2023 | NUR MOBINUL ISLAM | 64.15 | 18.44 | 28.75 | 70
Total | [13 empty] | 169.11 | 112.31 | 66.41