## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Construction of Boundary Wall at 2nd Pump House Site for Bara- Akalpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000537/2021-2022 | 23/RSD | 04/01/2022 | 18/02/2022 | INDRAJIT SAHA | 3.23 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of HDPE Pipe line on right side of Sainthia Sultanpur Road for Bara Akalpur, Gumta & Akalpur mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000690/2021-2022 | 129/RSD | 11/03/2022 | 10/04/2022 | M/S UNIT CONSTRUCTION | 4.98 | 3.82 | 76.56 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of HDPE 160 mm dia distribution line near Head work site in Pachim Panchberia mouza under Bara Akulpur water supply scheme under Rampurhat sub division under Birbhum Division PHE Dte. | AE | JE1,JE2,JE3 | ORD/000697/2021-2022 | 111/RSD | 07/03/2022 | 06/04/2022 | ALPHA PROJECT | 4.68 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Western side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000674/2021-2022 | 114/RSD | 07/03/2022 | 22/03/2022 | M/S UNIT CONSTRUCTION | 4.34 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Eastern side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000673/2021-2022 | 113/RSD | 07/03/2022 | 22/03/2022 | M/S UNIT CONSTRUCTION | 4.96 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of HDPE Pipe line for Akalpur, Gumta mouzas for providing FHTC under Bara Akalpur Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000687/2021-2022 | 127/RSD | 11/03/2022 | 10/04/2022 | M/S UNIT CONSTRUCTION | 4.95 | 4.68 | 94.54 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Allied FHTC works along with laying pipe lines at diff mouzas within BARA-AKULPUR w/s Scheme under Rampurhat Sub- Division ,Birbhum Divition P.H.E. Dte | AE | JE1 | ORD/000001/2023-2024 | 1132/BHM | 10/04/2023 | 25/05/2023 | ABUL HASNAT | 6.97 | 6.93 | 99.39 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of HDPE Pipe line for Bara Akalpur & Benegram mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000689/2021-2022 | 128/RSD | 11/03/2022 | 10/04/2022 | M/S UNIT CONSTRUCTION | 4.97 | 4.69 | 94.33 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of HDPE Pipe line for ,Kundala, Itahata etc mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1,JE2,JE3 | ORD/000684/2021-2022 | 126/RSD | 11/03/2022 | 10/04/2022 | M/S UNIT CONSTRUCTION | 4.94 | 4.68 | 94.65 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 217/BHM | 02/02/2022 | 02/02/2022 | Resource Division | 10.17 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bara Akalpur Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE,JE1 | ORD/000007/2022-2023 | 748/BHM | 05/04/2022 | 28/02/2025 | TAPAS KUMAR SARKHEL | 80.34 | 57.37 | 71.41 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09365 | Retrofitting | Laying of Rising main with DI K9 for inter connection & bypass arrangement of DI pipe line for Bara- Akalpur PWSS under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE,JE1,JE2,JE3 | ORD/000578/2021-2022 | 26/RSD | 04/01/2022 | 03/02/2022 | TAPAS KUMAR SARKHEL | 1.76 | 0 | 0 | 100
Total | [13 empty] | 136.32 | 82.16 | 60.27