## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Balance work of distribution pipeline including extention of pipeline along with FHTC and restoration of roads alongwith Construction of 500 M³ capacity 20.00 Mtr. staging height RCC Over Head Reservoir at Sadasibhpur W/S Scheme within Nalhati Sub-Division under Birbhum Division, P.H.E. Dte.(Sl. No.3) | AE | JE1 | ORD/000385/2022-2023 | 2857/BHM | 22/12/2022 | 01/07/2024 | SUPER SKILL | 175.35 | 60.71 | 34.62 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Restoration of concrete road including dismantling of Water Supply Scheme For Sadashibpur and it's adjoining Mouzas under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE1 | ORD/000105/2022-2023 | 356/AE/NSD | 20/07/2022 | 18/09/2022 | SUPER SKILL | 4.83 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Balance work for Pump House at Head Work site of Sadashibpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000686/2021-2022 | 168/AE/NSD | 22/03/2022 | 06/04/2022 | SUBHRANIL DAS | 0.83 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sadashibpur (Bisor) Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE1 | ORD/000018/2022-2023 | 822/BHM | 13/04/2022 | 12/06/2022 | QUAZI SIRAJUL ISLAM. | 94.04 | 61.3 | 65.18 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Balance works of Laying Distribution system at Sadasibpur, Kendishta, Chhatina and Amudda habitations under Sadashibpur W/S Scheme under Nalhati Sub-Division, within Birbhum Division P.H.E Dte.. (SL.No.5) | AE | JE1 | ORD/000826/2021-2022 | 498/BHM | 02/03/2022 | 16/04/2022 | SUPER SKILL | 47 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Supply & delivery of Sluice Valve for Sadashibpur (Bishor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-03) | AE(HQ) |  | ORD/000132/2022-2023 | 1243/BHM | 03/06/2022 | 18/06/2022 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Supply & delivery of Sluice Valve for augmentation of Sadashibpur (Bisor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-03) | AE(HQ) |  | ORD/000805/2021-2022 | 715/BHM | 31/03/2022 | 15/04/2022 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09366 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 213/BHM | 02/02/2022 | 02/02/2022 | Resource Division | 15.63 | 0 | 0 | 0
Total | [13 empty] | 347.66 | 122.01 | 35.09