## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Allied works for construction of pipe culvart, land development and temporary approach road at H/W site of JHIKADDA PWSS under Rampurhat Sub Division.PHE Dte. | AE | JE,JE1 | ORD/000534/2021-2022 | 20/RSD | 04/01/2022 | 03/02/2022 | ABHOY CHARAN GHOSH | 4.74 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Laying of HDPE Pipe line for Krishnanagar mouzas under Jhikadda Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000678/2021-2022 | 103/RSD | 07/03/2022 | 06/04/2022 | ABHOY CHARAN GHOSH | 4.96 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Laying of Rising main with DI pipe line for inter connection and bypass arrangement for Jhikadda water supply scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000535/2021-2022 | 21/RSD | 04/01/2022 | 03/02/2022 | KALYAN PAL | 1.65 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Construction of Boundary Wall & Internal path way at 2nd Site for JHIKADDA PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000536/2021-2022 | 22/RSD | 04/01/2022 | 18/02/2022 | ABHOY CHARAN GHOSH | 4.33 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jikadda Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte (Sl. No.3) | AE | JE1 | ORD/000008/2022-2023 | 821/BHM | 13/04/2022 | 12/06/2022 | KAZI EMDADUL HAQUE | 55.12 | 54.62 | 99.09 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. | SM/09368 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 216/BHM | 02/02/2022 | 02/02/2022 | Resource Division | 6.64 | 0 | 0 | 0
Total | [13 empty] | 77.44 | 54.62 | 70.53