## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | Retrofitting | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Danghara Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000652/2021-2022 | 131/AE/NSD | 09/03/2022 | 08/04/2022 | QUAZI SIRAJUL ISLAM. | 4.8 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | Retrofitting | Construction of Pump House of 5.40mtr. x 3.6mtr. size with sanitary and water supply arrangements at DHANGHARA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000899/2021-2022 | 17/AE/NSD | 17/01/2022 | 18/03/2022 | QUAZI SIRAJUL ISLAM. | 4.99 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Danghara under Danghara Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.4) | AE | JE2 | ORD/000208/2022-2023 | 2002/BHM | 15/09/2022 | 14/11/2022 | NUR MOBINUL ISLAM | 70.94 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09370 | Retrofitting | Extension of distribution Pipe line including FHTC Work along with restoration of road of Danghara Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte (Sl.No.4) | AE | JE2 | ORD/000559/2022-2023 | 874/BHM | 21/03/2023 | 20/05/2023 | QUAZI SIRAJUL ISLAM. | 29.28 | 0 | 0 | 50
Total | [13 empty] | 110 | 0 | 0