## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte. (Sl. No.1) | AE | JE3 | ORD/000242/2022-2023 | 2165/BHM | 28/09/2022 | 28/10/2022 | OM ENTERPRISE | 34.22 | 0 | 0 | 90
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Laying of Rising main with DI pipe line for inter connection of 3 Nos TW for Belera Piped Water Supply Scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000696/2021-2022 | 110/RSD | 07/03/2022 | 06/05/2022 | MD. SHAHA JAMAL | 4.52 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Sinking of 01 Nos (3rd TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000695/2021-2022 | 108/RSD | 07/03/2022 | 06/04/2022 | SK FAQHRUL AMIN | 4.85 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Sinking of 01 Nos (1st TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000694/2021-2022 | 107/RSD | 07/03/2022 | 06/04/2022 | SK FAQHRUL AMIN | 4.85 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Supply and delivery of Sluice Valve & Duck Foot Bend for Belera W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | AE | JE3 | ORD/000765/2021-2022 | 376/BHM | 21/02/2022 | 08/03/2022 | SSPR VALVE MANUFACTURING PVT LTD | 6.71 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. | SM/09371 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Belera Water Supply Scheme within Rampurhat Sub-Division, Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE3 | ORD/000005/2022-2023 | 747/BHM | 05/04/2022 | 04/06/2022 | S K CONSTRUTION | 73.03 | 0 | 0 | 100
Total | [13 empty] | 128.17 | 0 | 0