## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Purandarpur W/S Scheme (Sl. No.-06) | AE |  | ORD/000614/2020-2021 | 1826/BHM | 31/12/2020 | 31/12/2021 | PRANAB KUMAR MONDAL | 2.91 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Allied work for Laying distribution system for proposed augmentation scheme for Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE | JE1 | ORD/000115/2023-2024 | 2076/BHM | 08/06/2023 | 07/08/2023 | M/S GOUTAM DAS | 56.35 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 489/BHM | 02/03/2022 | 02/03/2022 | Resource Division | 25.74 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 215/BHM | 02/02/2022 | 02/02/2022 | Resource Division | 16.6 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 2290/BHM | 20/10/2022 | 20/10/2022 | Resource Division | 5.93 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1115/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 10.28 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Purandarpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE1 | ORD/000016/2023-2024 | 1215/BHM | 12/04/2023 | 12/01/2024 | M/S GOUTAM DAS | 128.59 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (02 nos.) 125 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000134/2023-2024 | 2269/BHM | 13/07/2023 | 12/08/2023 | PRANAB KUMAR MONDAL | 5.6 | 0 | 0 | 100
9 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Replacement of voltage correction device at Purandarpur PH-I water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Purandarpur W/S Scehem) | Assistant Engineer-III | Junior Engineer | ORD/000695/2023-2024 | 1360/AE-III | 17/10/2023 | 01/11/2023 | QUAZI NOZRUL ISLAM | 2.05 | 0 | 0 | 100
10 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Additional works for installation of submersible pumping machineries at Aug. of purandarpur water supply scheme Block- Suri-II under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000310/2024-2025 | 1880/BOL.MD | 05/08/2024 | 19/09/2024 | SATYAJIT GHOSH | 7.27 | 0 | 0 | 100
11 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | New service connection at aug. of Purandarpur PWSS. |  |  | BILL/02317/2023-2024 | BP-23-24-358 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.59 | 0 | 0 | 0
12 | BIRBHUM |  | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Laying distribution system for proposed augmentation scheme for purandarpur piped water supply scheme under Birbhum Sadar sub division PHE Dte. | AE | JE1 | ORD/000394/2022-2023 | 1026/BHM | 12/05/2022 | 23/01/2026 | M/S GOUTAM DAS | 387.66 | 290.54 | 74.95 | 95
13 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme | SM/09437 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Purandarpur water supply scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000007/2023-2024 | 716/Bol.MD | 19/04/2023 | 01/09/2025 | SATYAJIT GHOSH | 24.44 | 16.88 | 69.07 | 100
Total | [13 empty] | 680.01 | 307.42 | 45.21