## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply & delivery of sluice valve for Augmentation of Rajnagar W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-01) | AE(HQ) |  | ORD/000703/2021-2022 | 421/BHM | 24/02/2022 | 11/03/2022 | UJJWAL DAS | 4.86 | 4.86 | 100 | 100
2 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Repairing of the Pump House & CWR of the Rajnagar Pipe Water Supply under RWS Birbhum Sub-Division,PHE Dte. Suri, Birbhum. | AE | JE | ORD/000773/2021-2022 | 33/BH | 09/03/2022 | 08/04/2022 | RANJIT GHOSH | 0.76 | 0.7 | 92.85 | 50
3 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | repairing of the Pump house & C.W.R of the Rajnagar Pipe Water Supply Scheme under Birbhum Division, P.H.E .Dte, Suri , Birbhum. | AE | JE | ORD/000832/2021-2022 | 33/BH | 09/03/2022 | 08/04/2022 | RANJIT GHOSH | 0.76 | 0 | 0 | 50
4 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000359/2021-2022 | 592/AE/NSD | 23/11/2021 | 07/01/2022 | MD ASIF ALI | 4.82 | 0 | 0 | 50
5 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Trial Bore and Sinking for 03 nos. 200mm dia. Tubewell of 5m depth with horizontal strainer on the river Bed of Kuskorini under Rajnagar Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE2 | ORD/000506/2022-2023 | 270/BSSD | 11/11/2022 | 26/11/2022 | INDRANIL DUTTA | 4.84 | 4.84 | 99.95 | 100
6 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Laying distribution system for proposed augmentation scheme for Rajnagar Piped Water Supply Scheme under Rajnagar Block, under Birbhum Division, PHE Dte. (Sl. No.8) | AE | JE2 | ORD/000502/2021-2022 | 94/BHM | 21/01/2022 | 20/07/2022 | UJJWAL DAS | 315.1 | 292.97 | 92.98 | 100
7 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Construction of Boundary Wall with drain at Pump House & CWR of Rajnagar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.10) | AE | JE | ORD/000402/2022-2023 | 32/BHM | 04/01/2023 | 18/02/2023 | SYED GOLAM ZILANI | 9.18 | 8.2 | 89.33 | 100
8 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Daspara under Nakash Village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte.(Sl. No. -07) | AE | JE2 | ORD/000578/2022-2023 | 219/BSSD | 21/09/2022 | 06/10/2022 | UJJWAL DAS | 4.98 | 4.98 | 99.95 | 100
9 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Idgacha under Nakash village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. (Sl. No. -01) | AE | JE2 | ORD/000577/2022-2023 | 213/BSSD | 21/09/2022 | 06/10/2022 | UJJWAL DAS | 4.95 | 4.94 | 99.88 | 100
10 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Rajnagar W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE1 | ORD/000014/2023-2024 | 1256/BHM | 17/04/2023 | 12/01/2024 | M/S KRIPASINDHU GHOSH & CO. | 128.12 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Additional pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area except Daspara & Idgacha village of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE | JE3 | ORD/000104/2023-2024 | 1724/BHM | 12/05/2023 | 26/06/2023 | UJJWAL DAS | 14.53 | 0 | 0 | 0
12 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1110/BHM | 10/04/2023 |  | Resource Division | 14.64 | 0 | 0 | 0
13 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Providing Electro-mechanical accessories and others at low lift site for Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000236/2023-2024 | 1412/Bol.MD | 10/07/2023 | 24/08/2023 | AMITAVA CHAKRABORTY | 18.99 | 18.99 | 100 | 0
14 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply and Installation of Pumping Machineries at Matiara Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED. | Assistant Engineer-III | Junior Engineer | ORD/000239/2023-2024 | 1420/Bol.MD | 10/07/2023 | 09/08/2023 | M/S SANTI CONSTRUCTION | 6.68 | 5.79 | 86.74 | 0
15 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply and Installation of Pumping Machineries at ISGARA Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED | Assistant Engineer-III | Junior Engineer | ORD/000238/2023-2024 | 1413/BOL.MD | 10/07/2023 | 09/08/2023 | RAJIB GHOSH | 6.73 | 6.67 | 99.16 | 30
16 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2021-2022 | 487/BHM | 02/03/2022 |  | Resource Division | 30.25 | 0 | 0 | 0
17 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 193/BHM | 01/02/2022 |  | Resource Division | 25.77 | 0 | 0 | 0
18 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 214/BHM | 02/02/2022 |  | Resource Division | 21.82 | 0 | 0 | 0
19 | BIRBHUM |  | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Balance work for laying of pipe line including FHTC for augmentation of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE |  | ORD/000111/2023-2024 | 1876/BHM | 31/05/2023 | 30/07/2023 | OM ENTERPRISE | 56.94 | 48.06 | 84.41 | 100
20 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Modification of MCC panel of Isgara Mini water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001113/2023-2024 | 1658/AE-III | 22/12/2023 | 28/12/2023 | RAJIB GHOSH | 0.16 | 0 | 0 | 100
21 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply & delivery of Cable for Aug. Rajnagar water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001163/2023-2024 | 296/AE-III | 22/02/2024 | 03/03/2024 | SATYAJIT GHOSH | 3.86 | 1.93 | 50 | 100
22 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Replacement of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001199/2023-2024 | 368/BOL.MD | 06/03/2024 | 05/04/2024 | GOENKA ENTERPRISE | 14.34 | 7.17 | 50 | 0
23 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Rajnagar water supply scheme (Block- Rajnagar) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001169/2023-2024 | 301/AE-III | 22/02/2024 | 03/03/2024 | HINDOL ROY | 4.56 | 4.56 | 100 | 100
24 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply delivery & installation of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000521/2023-2024 | 2264/Bol.MD | 14/09/2023 | 29/10/2023 | CINZANO | 15.85 | 13.58 | 85.68 | 100
25 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Replacement of voltage correction device at Khoyrasole (Churur) water supply scheme (AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME) under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/001062/2023-2024 | 33/BOL.MD | 10/01/2024 | 09/02/2024 | S.DUTTA | 15.87 | 15.87 | 100 | 100
26 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply and Delivery of high lift pumping Machinery for Augmentation of Rajnagar and other water supply scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001311/2023-2024 | 605/AE-III | 27/03/2024 | 03/04/2024 | M/S M3 SOLUTION | 2.75 | 1.37 | 50 | 100
27 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply & delivery of High lift pumping machinery at store for Aug. Rajnagar and others water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001168/2023-2024 | 300/AE-III | 22/02/2024 | 03/03/2024 | SWAPAN BANERJEE | 2.75 | 1.37 | 50 | 100
28 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Testing and refilling of empty chlorine gas cylinder of Rajnagar and adjoining mouzas & Different Rural water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001172/2023-2024 | 302/AE-III | 22/02/2024 | 22/04/2024 | UNIVERSAL ENTERPRISES | 4.84 | 0 | 0 | 60
29 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply and delivery of outdoor type pump controller unit for Augmentation of Rajnagar under Ahmadpur PWSS in Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000059/2024-2025 | 1345/Bol.MD | 03/05/2024 | 17/06/2024 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 10.03 | 50 | 100
30 | BIRBHUM |  | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. | SM/09438 | Augmentation | Supply, delivery and installation of of Voltage correction device at panchiara water supply scheme( with in Rajnagar Augmentation Water Supply , Block : Rajnagar), under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000489/2023-2024 | 2245/Bol.MD | 13/09/2023 | 12/11/2023 | M/S P.P ELECTRICALS | 23.98 | 11.08 | 46.21 | 30
Total | [13 empty] | 783.73 | 467.97 | 59.71