## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. | SM/09490 | Retrofitting | Construction of boundary wall at Panchara OHR site of Panchara PWSS under Birbhum Sadar Sub-Division, PHE Dte. (Sl. No.09) |  |  | ORD/000662/2020-2021 | 949/BHM | 12/08/2020 | 26/09/2020 | BHABANI ENTERPRISE | 4.97 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. | SM/09490 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Panchra under Panchra Water Supply Water Supply Scheme within Birbhum Division, PHE Dte. (Sl. No.9) | AE | JE | ORD/000365/2022-2023 | 2773/BHM | 14/12/2022 | 12/02/2023 | MANASH GHOSH | 93.92 | 0 | 0 | 0
Total | [13 empty] | 98.89 | 0 | 0