## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | Retrofitting | Surging of 2 nos. existing Tube wells and other ancillary works at Kurumgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000639/2021-2022 | 694/AE/NSD | 30/12/2021 | 14/01/2022 | MD SURAJ ALI | 0.94 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kurumgram Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.13) | AE | JE2 | ORD/000420/2021-2022 | 2109/BHM | 17/12/2021 | 15/02/2022 | M/S MD AMINUL ISLAM | 76.13 | 76.13 | 100 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | Retrofitting | Replacement including extension of pipe line with FHTC to different habitations of kurumgram village including 200 mm PVC tube well & restoration of roads at Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHE Dte. | AE | JE2 | ORD/000370/2022-2023 | 1429/BHM | 05/07/2022 | 03/09/2022 | MD SURAJ ALI | 40.52 | 30.97 | 76.43 | 95
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | Retrofitting | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer of Head Work site of Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000108/2022-2023 | 361/AE/NSD | 21/07/2022 | 04/09/2022 | MD SURAJ ALI | 4.84 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. | SM/09491 | Retrofitting | Emergent repairing of pipeline with FHTC including road restoration in Kurumgram PWSS under Nalhati Sub-Division, within Birbhum Division PHE Dte. | AE | JE1 | ORD/000681/2024-2025 | 54/NSD | 12/02/2025 | 12/03/2025 | MD SURAJ ALI | 0.97 | 0 | 0 | 100
Total | [13 empty] | 123.41 | 107.1 | 86.79