## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Dubrajpur Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 08) | AE | JE | ORD/000404/2021-2022 | 381/BSSD | 10/12/2021 | 30/12/2021 | RANJIT GHOSH | 0.99 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional Household Tap Connection (FHTC) for AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Labpur Zone-I & Zone-II Water Supply Scheme within Labpur Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 08). | AE | JE | ORD/000853/2021-2022 | 71/BSD | 03/03/2022 | 13/03/2022 | ANKITA CHAKRABORTY | 1.09 | 0 | 0 | 50
3 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 18 (Eighteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Bolpur Sriniketan Development Block under Birbhum Division P.H.E.Dte. (Sl. No.17) | AE | JE | ORD/000373/2022-2023 | 2794/BHM | 15/12/2022 | 29/01/2023 | PRATIMA CONSTRUCTION | 11.1 | 0 | 0 | 10
4 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Alunda & Nagari G.P. within the command area of Suri-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.1) | AE | JE | ORD/000375/2022-2023 | 2796/BHM | 15/12/2022 | 29/01/2023 | MITA DAS DOM | 12.96 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Kaitha-I within the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. (SL.No.5) | AE | JE | ORD/000286/2022-2023 | 2308/BHM | 21/10/2022 | 05/12/2022 | DUBE ENTERPRISE | 17.3 | 0 | 0 | 97
6 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos Anganwadi Center having no Electric Power Connection under Illambazar, Bilati & Nanasole GP within the command area of Illambazar Development Block under Birbhum Division P.H.E. Dte. | AE | JE | ORD/000318/2022-2023 | 2510/BHM | 17/11/2022 | 01/01/2023 | PRATICK KUMAR GHOSH | 17.02 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Barla G.P. within the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. | AE |  | ORD/000295/2022-2023 | 2499/BHM | 17/11/2022 | 01/01/2023 | MAHALAXMI CONSTRUCTION | 17.31 | 0 | 0 | 0
8 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 24 (Twenty Four) nos. Anganwadi Centre having no Electric Power Connection under Deucha, Angargar & Kapista G.P. within the command area of MD. Bazar Development Block under Birbhum Division P.H.E. Dte.Total Number of Anganwadi Center -24, (Sl. No.9) | AE,AE(HQ) | JE | ORD/000337/2022-2023 | 2609/BHM | 24/11/2022 | 08/01/2023 | SHIRSHENDU MUKHERJEE | 15.21 | 0 | 0 | 0
9 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos. Anganwadi Center having no Electric Power Connection JOydev Kenduli, Ghurisha, & Batikar G.P. within the command area of Illambazar Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.14) | AE | JE | ORD/000311/2022-2023 | 2489/BHM | 16/11/2022 | 31/12/2022 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 16.63 | 0 | 0 | 39
10 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 10 (Ten) Nos Anganwadi Center having no Electric Power Connection within the command area of Murarai-II Development Block under Birbhum Division P.H.E.Dte. (Sl. No.13) | AE | JE | ORD/000384/2022-2023 | 2886/BHM | 22/12/2022 | 05/02/2023 | HARUN AR RASHID | 6.18 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 16 (Sixteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Murarai-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.12) | AE | JE | ORD/000387/2022-2023 | 2918/BHM | 27/12/2022 | 10/02/2023 | MD ASIF ALI | 9.88 | 0 | 0 | 0
12 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 26 (Twenty Six) Nos Anganwadi Center having no Electric Power Connection within the command area of Dubrajpur Development Block under Birbhum Division P.H.E.Dte. (Sl. No.18) | AE | JE | ORD/000389/2022-2023 | 2916/BHM | 27/12/2022 | 10/02/2023 | RUBAL CONSTRACTION | 16.06 | 0 | 0 | 0
13 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 12 (Twelve) Nos Anganwadi Center having no Electric Power Connection within the command area of Nalhati-II Development Block under Birbhum Division P.H.E.Dte.(Sl. No.14) | AE |  | ORD/000388/2022-2023 | 2917/BHM | 27/12/2022 | 10/02/2023 | HIMANGSU SEKHAR SARKAR | 7.47 | 0 | 0 | 0
14 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Pachra & Parsundi G.P. within the command area of Khoyrasole Development Block under Birbhum Division P.H.E.Dte. Total Number of Anganwadi Center -28, (Sl. No.13) | AE | JE | ORD/000336/2022-2023 | 2607/BHM | 24/11/2022 | 08/01/2023 | UTPAL DEY | 17.81 | 0 | 0 | 0
15 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 23 (Twenty Three) Nos. Anganwadi Center having no Electric Power Connection under within Banior, Bautia, Kalitha & Kaitha-II G.P. the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. | AE |  | ORD/000304/2022-2023 | 2502/BHM | 17/11/2022 | 01/01/2023 | RAJA CONSTRUCTION | 14.61 | 0 | 0 | 48
16 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) nos. Anganwadi Center having no Electric Power Connection under Ahmadpur and Mathpalsa G.P. within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. | AE | JE1 | ORD/000331/2022-2023 | 2599/BHM | 23/11/2022 | 07/01/2023 | JAYANTA BARAL | 11.73 | 0 | 0 | 0
17 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) Nos Anganwadi Center having no Electric Power Connection under Barasota within the command area of Nanoor Development Block under Birbhum Division P.H.E.Dte. (Sl. No.5) | AE | JE | ORD/000397/2022-2023 | 27/BHM | 04/01/2023 | 18/02/2023 | GOURANGA MONDAL | 11.73 | 0 | 0 | 0
18 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 26 (Twenty Six) Nos Anganwadi Center having no Electric Power Connection under Labpur-I & Labpur-II GP within the command area of Labpur Development Block under Birbhum Division P.H.E.Dte. | AE | JE | ORD/000298/2022-2023 | 2608/BHM | 24/11/2022 | 08/01/2023 | MS KAZIMEHERUDDIN | 16.35 | 0 | 0 | 0
19 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Anganwadi Center having no Electric Power Connection under Deriapur G.P. within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. (Sl. No.7) | AE | JE | ORD/000487/2022-2023 | 292/BHM | 01/02/2023 | 18/03/2023 | M/S S.N CONSTRUCTION | 12.36 | 0 | 0 | 0
20 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 4 (Four) Nos Anganwadi Center having no Electric Power Connection within the command area of Rampurhat-II Development Block under Birbhum Division P.H.E.Dte. (Sl. No.16) | AE | JE | ORD/000511/2022-2023 | 522/BHM | 20/02/2023 | 06/04/2023 | MS SANTI CONSTRUCTION | 2.47 | 0 | 0 | 0
21 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Survey for Functional Household Tap Connection (FHTC) at different School and Aganwadi Centre in Nalhati-I & Nalhati-II Block under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000234/2021-2022 | 423/AE/NSD | 23/08/2021 | 07/09/2021 | JOY CHAND MAL | 0.09 | 0 | 0 | 13
22 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Survey for Functional Household Tap Connection (FHTC) at different School and Aganwadi Centre in Murarai-I & Murarai-II Block under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000235/2021-2022 | 424/AE/NSD | 23/08/2021 | 07/09/2021 | JOY CHAND MAL | 0.09 | 0 | 0 | 37
23 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Sainthia Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | AE | JE | ORD/000432/2021-2022 | 400/BSSD | 14/12/2021 | 03/01/2022 | SUBHRADIP SARKAR | 0.99 | 0 | 0 | 50
24 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Rajnagar Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 10) | AE | JE | ORD/000405/2021-2022 | 382/BSSD | 10/12/2021 | 30/12/2021 | SUBHANKAR ROY | 0.99 | 0 | 0 | 49
25 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Illambazar (Illambazar & Daronda) within Ruppur & Illambazar G.P.under Bolpur Sub-Division within Birbhum Division, PHED | AE | JE1 | ORD/000459/2021-2022 | 16/BSD | 11/01/2022 | 26/01/2022 | GANAPATI ENGINEERING CORP. | 1.97 | 0 | 0 | 48
26 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Primary School having Electric Power Connection within the command area of MD. Bazar Development Block under Birbhum Division P.H.E.Dte.(Sl. No.4) | AE |  | ORD/000356/2022-2023 | 2708/BHM | 07/12/2022 | 21/01/2023 | SOUMEN CHATTERJEE | 18.6 | 0 | 0 | 100
27 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 16 (Sixteen) Nos. Primary School having Electric Power Connection within the command area of Nanoor Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.1) | AE | JE | ORD/000294/2022-2023 | 2846/BHM | 22/12/2022 | 05/02/2023 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.31 | 0 | 0 | 100
28 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Primary School having Electric Power Connection within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. (Sl. No.2) | AE |  | ORD/000470/2022-2023 | 204/BHM | 19/01/2023 | 05/03/2023 | PARTHA PRATIM ACHARYA | 18.21 | 0 | 0 | 100
29 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Extension of Pipe line at Husnabad and Lambodarpur for providing connection to 3 nos A.W.C's, supply water to Husnabad Muslimpara & restoration of damaged pipeline at Sabujpally (JL No. - 106) of Karidhya Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 08) | AE | JE | ORD/001085/2021-2022 | 389/BSSD | 10/12/2021 | 25/12/2021 | M/S C.P. CONCERN | 1.67 | 0 | 0 | 100
30 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 14 (Fourteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Mayureswar-II Development Block under Birbhum Division P.H.E.Dte.Total Number of Anganwadi Center -14, (Sl. No.18) | AE | JE | ORD/000335/2022-2023 | 2606/BHM | 24/11/2022 | 08/01/2023 | PRANAB KUMAR MONDAL | 8.08 | 0 | 0 | 100
31 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Mallickpur & Khatanga G.P. within the command area of Suri-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.3) | AE | JE | ORD/000372/2022-2023 | 2793/BHM | 15/12/2022 | 29/01/2023 | SRAMIC MANGAL CO OP LABOUR CONT AND CONST SOCIETY LTD | 12.97 | 0 | 0 | 100
32 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 24 (Twenty Four) Nos. Primary School having Electric Power Connection within the command area of Bolpur Sriniketan, Dubrajpur, Nalhati-I & Suri-II Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.6) | AE | JE | ORD/000291/2022-2023 | 2443/BHM | 03/11/2022 | 18/12/2022 | G.S CONSTRUCTION AND CO. | 21.73 | 0 | 0 | 85
33 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos. Anganwadi Center having no Electric Power Connection under Kendgore, Khoyrasole & Hazratpur G.P. within the command area of Khoyrasole Development Block under Birbhum Division P.H.E.Dte. | AE | JE | ORD/000292/2022-2023 | 2434/BHM | 02/11/2022 | 17/12/2022 | B.M.SARKAR | 16.55 | 0 | 0 | 42
34 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Anganwadi Center having no Electric Power Connection under Kendua & Domdoma within the command area of Suri-II Development Block under Birbhum Division P.H.E.Dte(Sl. No.10) | AE | JE | ORD/000368/2022-2023 | 2786/BHM | 14/12/2022 | 28/01/2023 | M/S.CHANDRANATH MUKHERJEE | 12.36 | 0 | 0 | 0
35 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos. Primary School having Electric Power Connection within the command area of Murarai-I Development Block under Birbhum Division P.H.E.Dte. | AE | JE | ORD/000351/2022-2023 | 2653/BHM | 01/12/2022 | 15/01/2023 | KAZI EMDADUL HAQUE | 19.51 | 0 | 0 | 100
36 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Kirnahar-I, Kirnahar-II & Nonnagar Kadda within the command area of Nanoor Development Block under Birbhum Division P.H.E.Dte.(Sl. No.6) | AE | JE | ORD/000403/2022-2023 | 33/BHM | 04/01/2023 | 18/02/2023 | KHOKAN SAHA | 12.98 | 0 | 0 | 0
37 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) Nos Anganwadi Center having no Electric Power Connection under Koma and Purandarpur within the command area of Suri-II Development Block under Birbhum Division P.H.E.Dte. | AE | JE | ORD/000332/2022-2023 | 2656/BHM | 01/12/2022 | 15/01/2023 | BARDHAMAN AQUA ENGINEERING | 11.5 | 0 | 0 | 0
38 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing necessary water supply arrangement at 17 (Seventeen) Nos Primary School having Electric Power Connection within the command area of Labpur Development Block under Birbhum Division P.H.E.Dte.(Sl. No.5) | AE | JE | ORD/000473/2022-2023 | 223/BHM | 20/01/2023 | 06/03/2023 | AVIJIT CHANDA | 15.88 | 0 | 0 | 45
39 | BIRBHUM |  | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division | SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Khayrasole Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. | AE | JE | ORD/001198/2021-2022 | 383/BSSD | 10/12/2021 | 30/12/2021 | HIRANMAY GHOSH | 0.99 | 0 | 0 | 100
Total | [13 empty] | 425.77 | 0 | 0