## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health Centre, Govt. institution & Household of Habitation-Damonpur, Mouja Ramkantapur (139) from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - X & Zone - XIII within Sian Muluk G.P. of Bolpur Sub -Division under Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000413/2021-2022 | 447 /BSD | 10/12/2021 | 09/01/2022 | SUBHRADIP SARKAR | 4.85 | 5.72 | 117.79 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone- XI Indo -German Water Supply Scheme in Bolpur Sub-Division within Birbhum Division, PHED. | AE,Assistant Engineer | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000471/2021-2022 | 2165/BHM | 24/12/2021 | 22/02/2022 | SYED HASMAT ALI | 26.72 | 16.29 | 60.96 | 80
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at MULUK (121) village and Arazi Muluk (125) Village (Part) within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone- XIII) under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000317/2021-2022 | 385/BSD | 07/10/2021 | 06/11/2021 | SYED HASMAT ALI | 4.85 | 4.71 | 97.26 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-XIII (Indo-German) Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte (Sl. No. 09) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000474/2021-2022 | 2163/BHM | 24/12/2021 | 22/02/2022 | BISWARUP GHOSH | 30.65 | 28.73 | 93.72 | 99
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000516/2021-2022 | 400/BSD | 25/10/2021 | 04/11/2021 | JAYANTA BARAL | 0.96 | 0.96 | 99.61 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System of (Zone ¿ VIII & Zone ¿ IX) under Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000515/2021-2022 | 398/BSD | 25/10/2021 | 04/11/2021 | GANAPATI ENGINEERING CORP. | 0.97 | 0.76 | 78.52 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-IX (Indo German) water supply w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.11) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000636/2021-2022 | 1659 / BHM | 30/09/2021 | 29/11/2021 | HIMANGSU SEKHAR SARKAR | 37.25 | 15.28 | 41.01 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VII) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 02) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000627/2021-2022 | 239/BSD | 16/07/2021 | 15/08/2021 | M/S HORIZEN | 0.97 | 0 | 0 | 0
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Leftout School & Aganwadi Centre with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 07). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000647/2021-2022 | 70/BSD | 03/03/2022 | 18/03/2022 | MS AD ENTERPRISE | 2.53 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - X and Zone - XIII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000624/2021-2022 | 401/BSD | 25/10/2021 | 04/11/2021 | SUBHRADIP SARKAR | 0.97 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 01) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000630/2021-2022 | 237/BSD | 16/07/2021 | 15/08/2021 | M/S HORIZEN | 0.97 | 0 | 0 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aidded Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000024/2021-2022 | 231/BSD | 07/07/2021 | 22/07/2021 | M/S HORIZEN | 0.1 | 0.1 | 100 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XI of Sian Muluk G.P.under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000329/2021-2022 | 399/BSD | 25/10/2021 | 04/11/2021 | SK.RUHUL AMIN | 0.97 | 0.65 | 67.42 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution System in in Sian MULUK G.P. (Vill. Baidyanathpur, Dwarkanathpur, Purba Islampur, Sahajpur, Sian) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000314/2021-2022 | 382/BSD | 07/10/2021 | 06/11/2021 | ARABINDA GHOSH | 4.83 | 4.82 | 99.92 | 100
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at Gayeshpur and Bergram under Sian-Muluk Gram Panchayet within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000255/2021-2022 | 310/BSD | 24/08/2021 | 13/09/2021 | IMAGIN | 0.38 | 0.38 | 100 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Surul Mouza, JL : 104 (Habitation - MOLDANGA) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - VIII under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000319/2021-2022 | 380/BSD | 07/10/2021 | 06/11/2021 | PRATICK KUMAR GHOSH | 4.22 | 3.38 | 80 | 100
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in SHYAMBATI Mouza JL : 67 (Habitation - Shyambati, Subhaspally, Munnapara etc.) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project ( Indo- German ) Zone - IX under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000334/2021-2022 | 383/BSD | 07/10/2021 | 06/11/2021 | B. B. CONSTRUCTION | 4.69 | 4.3 | 91.59 | 100
18 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System within (Zone ¿ VII) of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000345/2021-2022 | 397/BSD | 25/10/2021 | 04/11/2021 | MS AD ENTERPRISE | 0.97 | 2.8 | 288.45 | 100
19 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation - Ramchandrapur, Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000716/2021-2022 | 75/BSD | 03/03/2022 | 02/04/2022 | MAA KANKALI ENTERPRISE | 4.83 | 4.7 | 97.27 | 100
20 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Additional remaining work of C.W.R .and development of land of C.W.R. site at Rasulpur (Near Ajoy River Bank) for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German). Zone - X under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No. - 12) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000607/2021-2022 | 456/BSD | 13/12/2021 | 12/01/2022 | MS B N ENTERPRISES | 4.14 | 0 | 0 | 100
21 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - XII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 08) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000605/2021-2022 | 78/BHM | 18/01/2022 | 19/03/2022 | SOUMEN CHATTERJEE | 26.72 | 25.55 | 95.6 | 100
22 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - VIII Indo German Water Supply Scheme in Bolpur Sub-Division undr Birbhum Division PHED. (Sl. 15) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000713/2021-2022 | 597/BHM | 21/03/2022 | 05/05/2022 | RADHARANI ENTERPRISE | 25.23 | 22.67 | 89.87 | 100
23 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation - Raipur Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 06). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000721/2021-2022 | 76/BSD | 03/03/2022 | 02/04/2022 | SEKH MAMTAZ HOSSAIN | 4.77 | 4.63 | 97.14 | 100
24 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - X) (2nd Phase : - Jay Krishnapur, Ramakantapur, Ramganj, Gulandi, Gahara etc.) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.: 09) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000813/2021-2022 | 347/BSD | 15/09/2021 | 15/10/2021 | IMAGIN | 0.97 | 0.97 | 100 | 100
25 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-VII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.14) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000669/2021-2022 | 578/bhm | 17/03/2022 | 01/05/2022 | ASHA ENTERPRISE | 25.13 | 25.02 | 99.58 | 100
26 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at NURPUR (Part) & Gheropara (Part) with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 03). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000082/2022-2023 | 252/BSD | 04/07/2022 | 03/08/2022 | CHAYAN KUMAR MONDAL | 4.81 | 4.81 | 99.9 | 100
27 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of Mouja Durgapur (143), Gitgram (144), Bara Simulia (145), Chota Simulia (145), Dakshin Gobindapur (151), Ramganja (152) & Panchshoa (142) etc. of Zone - X under Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo - German) in Bolpur Sub-Division within Birbhum Division PHE Dte. (Sl. No. - 3) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000097/2022-2023 | 1469/BHM | 11/07/2022 | 09/09/2022 | SACHIN KUMAR SARKAR | 38.19 | 33.65 | 88.11 | 100
28 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Retrofitting of pipe lines at Laichili Pukurpara, Mirdhapara, Mosjidpara and Korapara of GAYESHPUR Mouja for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 04). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000084/2022-2023 | 258/BSD | 07/07/2022 | 06/08/2022 | PRATICK KUMAR GHOSH | 4.82 | 4.8 | 99.66 | 100
29 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Habitation- Kankutia, village -KANKUTIA, G.P. - Raipur-Supur from existing Distribution System within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. (Sl. No.: 05). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000154/2022-2023 | 308/BSD | 16/08/2022 | 15/09/2022 | SEKH MAMTAZ HOSSAIN | 4.81 | 4.69 | 97.57 | 100
30 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Laying of Rising Main pipeline from Tube-well no. - II to new O.H.R. of Layekbazar with D.I. (K-9) pipe including inter-connection and extension of pipe line at Paruldanga, Choto Canalpar, Paruldanga Nishapati Colony, Nildanga Adibasipara, Rintoladanga (Dangapara), Jharnadanga etc. for providing FHTC within the command area for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. noo. - 11) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000950/2021-2022 | 455/BSD | 13/12/2021 | 12/01/2022 | GANAPATI ENGINEERING CORP. | 4.55 | 3.64 | 80.06 | 100
31 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Extension of pipeline to Madhakhara, Rasulpur & Haripur mouzas and Supplying & Laying of Rising Main & Distribution main with ERWMS pipe at Golamighat Bridge under ZONE-X for Augmentation of BOLPUR WATER SUPPLY, Sanitation & Health Education Project (INDO-GERMAN), within Bolpur Sub-Division under Birbhum Division, PHED.?(Sl. No.1) | AE | JE1,JE2,Bolpur Sub-Division | ORD/000952/2021-2022 | 1590/BHM | 22/09/2021 | 21/11/2021 | PRABHAT KUMAR MONDAL. | 43.05 | 0 | 0 | 100
32 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Retrofitting work of columns bracings shell wall top Dom etc and overall painting of overhead reservoir situated at boipur sub division phe campus of surul WS Scheme under Bolpur Sub Division within Birbhum Division PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000751/2020-2021 | 1682/BHM | 21/12/2020 | 19/02/2021 | M/S KRIPASINDHU GHOSH & CO. | 14.59 | 13.04 | 89.35 | 100
33 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Construction of Boundary Wall at CWR site Head Work site of Zone-III of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (124.00m long). (Sl.no. 07) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000700/2021-2022 | 2016/BHM | 31/12/2021 | 30/01/2022 | ABDUL SALEK MALLIK | 8 | 0 | 0 | 100
34 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution System in KANKALITALA G.P. Vill.: Layek Bazar, Adityapur, Uttar Narayanpur, Khosh Kadampur (Purbapara) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone -XII) under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000315/2021-2022 | 381/BSD | 07/10/2021 | 06/11/2021 | ARNAB CHANDRA | 4.83 | 4.83 | 99.98 | 100
35 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Construction of Boundary Wall at CWR site (Goalpara) of Zone-IX of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (155.00m long). (Sl.no. 08) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000699/2021-2022 | 2013/BHM | 31/12/2021 | 30/01/2022 | ABDUL SALEK MALLIK | 10.35 | 0 | 0 | 100
36 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Restoration of Cement Concrete road damage due to providing Functional Household Tap Connection (FHTC) from existing distribution system within Kankalitala Gram Panchayet (Vill. - Layek Bazar, Nildanga, Adityapur etc.) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) Zone-XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 09). | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000866/2021-2022 | 58/BSD | 22/02/2022 | 01/03/2022 | ARNAB CHANDRA | 0.8 | 0.55 | 68.62 | 92
37 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 220/BHM | 02/02/2022 | 02/02/2022 | Resource Division | 54.98 | 0 | 0 | 0
38 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 2209/BHM | 12/10/2022 | 12/10/2022 | Resource Division | 0.02 | 0 | 0 | 0
39 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Extension of 90 Mtr. dia. HDPE pipeline near Udyanpally OHR at Ward no. 6 (Six) under Zone - I for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 01) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000488/2021-2022 | 301/BSD | 19/08/2021 | 18/09/2021 | INDRAJIT DAS | 4.97 | 0 | 0 | 100
40 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Bolpur Water Supply, Sanitation & health education project (Indo-German) Zone-XII in Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000328/2022-2023 | 2271/BHM | 18/10/2022 | 17/11/2022 | SUPRIYA RAY | 25.56 | 0 | 0 | 100
41 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Mehidipur (105) village under Raipur-Supur Gram Panchayat within the Command area of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), Zone - VIII for Swajal Gram under Bolpur-Sriniketan Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. (Sl. No.7) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000474/2022-2023 | 224/BHM | 20/01/2023 | 06/03/2023 | B RAI CONSTRUCTION COMPANY | 57.78 | 6.63 | 11.48 | 100
42 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - IX Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 06) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000632/2021-2022 | 380/BHM | 21/02/2022 | 21/06/2022 | INDRAJIT DAS | 36.29 | 14.22 | 39.18 | 100
43 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone -X Indo-German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 13) | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000620/2021-2022 | 280/BHM | 09/02/2022 | 21/07/2022 | PINTU KHAN | 33.49 | 24.48 | 73.09 | 92
44 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mouja Haripur,(146), Rasulpur (147) and Upparkhara etc. Zone-X under Augmentation of Bolpur W/S Sanitation & Health Education Project (Indo-German) in Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3,JE4 | ORD/000330/2022-2023 | 2244/BHM | 17/10/2022 | 16/11/2022 | SUPRIYA RAY | 26.69 | 23.8 | 89.19 | 100
45 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. | SM/09792 | Retrofitting | Retrofitting works for providing functional household tap connection (FHTC) at Mahidapur village of Zone-VIII by Surging of existing 01 no tube well (Indo-German) along with connecting pipe line & Construction of Switch Room Cum Chlorine Room 2.25 mtr.X 3.00 mtr. Size near BITM (Gopalnagar mouzas) of Bolpur water supply scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 | ORD/000154/2024-2025 | 2614/BHM | 11/09/2024 | 10/12/2024 | INDRANIL DUTTA | 5.23 | 0 | 0 | 100
Total | [13 empty] | 603.43 | 311.56 | 51.63