## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Supply and installation of Voltage Correction device & other allied work at Augmentation of Tejhati water supply scheme under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000005/2023-2024 | 714/Bol.MD | 19/04/2023 | 03/06/2023 | STANDARD ELECTRICALS | 14.18 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2021-2022 | 486/BHM | 02/03/2022 | 02/03/2022 | Resource Division | 4.21 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1111/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 14.64 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Construction of 300 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Tejhati W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing) |  | JE2 | ORD/000085/2023-2024 | 1636/BHM | 02/05/2023 | 02/02/2024 | GOLAM RASUL | 86.89 | 0 | 0 | 40
5 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000685/2021-2022 | 167/AE/NSD | 22/03/2022 | 06/04/2022 | MOYTEC | 0.99 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Tejhati PWSS under Nalhati Sub- Division within Birbhum Division PHED | AE | JE2 | ORD/000135/2023-2024 | 2017/BHM | 06/06/2023 | 21/07/2023 | BHARAT CONSTRUCTION | 6.85 | 0 | 0 | 80
7 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Allied work of distribution Pipe line including FHTC Work along with restoration of road including dismantling work with jack pushing & Augur Boring for Augmentation of Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000291/2023-2024 | 3653/BHM | 25/08/2023 | 24/10/2023 | QUAZI SIRAJUL ISLAM. | 67.81 | 0 | 0 | 70
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000865/2023-2024 | 1363/AE-III | 17/10/2023 | 01/11/2023 | SINHA ELECTRICALS | 3.38 | 0 | 0 | 100
9 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Supply and Delivery of automatically controlled Chlorinator for Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000975/2023-2024 | 1449/AE-III | 17/11/2023 | 27/11/2023 | CINZANO | 3.27 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Augmentation of Tejhati PWSS | SM/10166 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Tezhati Piped Water Supply Scheme, Nalhati-I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.7) | AE | JE2 | ORD/000507/2022-2023 | 1150/BHM | 23/05/2022 | 28/02/2025 | QUAZI SIRAJUL ISLAM. | 168.84 | 0 | 0 | 62
Total | [13 empty] | 371.04 | 0 | 0