## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Augmentation of Nagari Piped Water Supply Scheme, Block-Suri-I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000470/2023-2024 | 2223/Bol.MD | 12/09/2023 | 11/11/2023 | HINDOL ROY | 23.52 | 0 | 0 | 50
2 | BIRBHUM |  | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1114/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 2.73 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 970/BHM | 27/03/2023 | 27/03/2023 | Resource Division | 11.88 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 3275/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 0.34 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Construction of 150 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying pipeline for Augmentation of Nagari w/s Scheme under Birbhum Sadar Sub-Division within Birbhum Division,P.H.E. Dte. (Sl. No.6) | AE | JE3 | ORD/000432/2022-2023 | 105/BHM | 11/01/2023 | 10/07/2023 | M/S KRIPASINDHU GHOSH & CO. | 189.64 | 0 | 0 | 75
6 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Replacement of Centrifugal Pumping Machinery and allide works at Karidhya water supply scheme (Suri-I) under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000540/2024-2025 | 3799/BOL.MD | 12/09/2024 | 12/10/2024 | WEST BENGAL ENGINEERING CO. | 10.68 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Trial Bore and Sinking for 03 nos. working 200mm dia. Tubewell of 6m depth each with horizontal strainer on the river Bed of Kuskurini and connecting pipe line etc. complete under Augmentation of Nagari Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | AE | JE3 | ORD/000509/2023-2024 | 652/BHM | 20/02/2024 | 05/04/2024 | INDRANIL DUTTA | 7.99 | 0 | 0 | 100
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Supply & delivery of 80mm dia Column Pipe for Augmentation of Nagari water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | Assistant Engineer-III | Junior Engineer | ORD/000499/2024-2025 | 1450./AE-III | 09/09/2024 | 16/09/2024 | VIBGYOR INFOTECH | 2.96 | 0 | 0 | 100
9 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme | SM/10312 | Augmentation | Quotation for new service connection at Augmentation of Nagari PWSS at SURI-I Block |  |  | BILL/00995/2024-2025 | BP-24-25-270 | 04/12/2024 | 04/12/2024 | WBSEDCL | 6.24 | 0 | 0 | 0
Total | [13 empty] | 255.97 | 0 | 0