## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | AE(HQ) | JE2 | ORD/000414/2023-2024 | 4292/BHM | 10/11/2023 | 10/12/2023 | MAKALI ENGINEERING CORPORATION | 9 | 9 | 100 | 100
2 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 913/BHM | 26/04/2022 | 26/04/2022 | Resource Division | 4.97 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 3274/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 0.34 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | AE(HQ) | JE2 | ORD/000468/2023-2024 | 500/BHM | 02/02/2024 | 03/03/2024 | MAKALI ENGINEERING CORPORATION | 9 | 9 | 100 | 100
5 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Ahmedpur water supply scheme under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000008/2023-2024 | 717/Bol.MD | 19/04/2023 | 03/06/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.19 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Ahmedpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. | AE | JE | ORD/000263/2023-2024 | 1103/BHM | 10/04/2023 | 10/01/2024 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 152 | 30.4 | 20 | 20
7 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (02 no.) 170 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Ahmedpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE | JE,JE1 | ORD/000119/2023-2024 | 1981/BHM | 05/06/2023 | 10/11/2024 | NEEL ENTERPRISE | 6.94 | 0 | 0 | 100
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Quotation for new service connection at Ahmedpur PWSS Low Lift site Under Rajnagar CCC |  |  | BILL/01693/2024-2025 | 103/02 | 18/07/2025 | 18/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.27 | 0 | 0 | 0
9 | BIRBHUM |  | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme | SM/10313 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Ahmedpur Piped Water Supply Scheme, Sainthia Block, under Birbhum Division, PHE Dte. (Sl. No.6) | AE | JE,JE1 | ORD/000358/2022-2023 | 1158/BHM | 23/05/2022 | 30/09/2025 | PASCON | 445.38 | 419.67 | 94.23 | 100
Total | [13 empty] | 673.08 | 468.06 | 69.54