## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Construction of Boundary wall at Pump House River Bank site under Pachiara Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division, P.H.E. Dte. (Sl. No. -19) |  |  | ORD/000123/2021-2022 | 250/BSSD | 03/08/2021 | 17/09/2021 | RANJIT GHOSH | 2.69 | 2.52 | 94.01 | 100
2 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Pachiara W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE3 | ORD/000015/2023-2024 | 1290/BHM | 18/04/2023 | 18/01/2024 | M/S GOUTAM DAS | 128.83 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 907/BHM | 26/04/2022 | 26/04/2022 | Resource Division | 4.36 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 946/BHM | 24/03/2023 | 24/03/2023 | Resource Division | 68.5 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1119/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 10.48 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 3282/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 1.37 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 2245/BHM | 07/07/2023 | 07/07/2023 | Resource Division | 2.85 | 0 | 0 | 0
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | WBSEDCL QUOTATION FOR PACHAIARA WS SCHEME |  |  | BILL/01364/2023-2024 | BP-23-24-146 | 28/11/2023 | 28/11/2023 | WBSEDCL | 0.02 | 0 | 0 | 0
9 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Providing and Installation of Electro-Mechanical equipments and other allied Works for Augmentation of PANCHIARA PWSS under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000451/2023-2024 | 2129/Bol.MD | 25/08/2023 | 23/11/2023 | SATYAJIT GHOSH | 96.79 | 72.3 | 74.7 | 50
10 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Laying of Rising Main Pipe line for the Augmentation of Pachiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000523/2023-2024 | 768/BHM | 01/03/2024 | 15/04/2024 | M/S JOY MAA BANAMALI | 6.37 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Construction of Drain and Valve Chamber Pachiara Water Supply Scheme at Rampur under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte.(Sl.No.5) | AE | JE | ORD/000543/2022-2023 | 134/BH | 15/06/2022 | 15/07/2022 | UTPAL DEY | 3.03 | 2.98 | 98.46 | 0
12 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (04 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Sal for the Augmentation of Panchiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000114/2023-2024 | 1982/BHM | 05/06/2023 | 05/07/2023 | AMIT KUMAR ROY | 5.7 | 3.85 | 67.52 | 100
13 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | WBSEDCL QUOTATION FOR PACHHIARA |  |  | BILL/01577/2023-2024 | BP-23-24-203 | 04/01/2024 | 04/01/2024 | WBSEDCL | 5.75 | 0 | 0 | 0
14 | BIRBHUM |  | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme | SM/10314 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Pachiara Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Division, PHE Dte.? (Sl. No.1) | AE | JE,JE2 | ORD/000248/2022-2023 | 1161/BHM | 23/05/2022 | 01/08/2025 | M/S GOUTAM DAS | 467.38 | 382.76 | 81.89 | 92
Total | [13 empty] | 804.11 | 464.42 | 57.76