## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (2 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000123/2023-2024 | 1984/BHM | 05/06/2023 | 05/07/2023 | INDRAJIT DUTTA. | 3.38 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Laying distribution system including FHTC for proposed Augmentation scheme for Mathpalsa Piped Water Supply Scheme , Sainthia Block under Birbhum Dvisision PHE DTE (Sl.No.2) | AE | JE3 | ORD/000338/2022-2023 | 1160/BHM | 23/05/2022 | 19/11/2022 | APURBA MONDAL | 144.13 | 141.16 | 97.94 | 100
3 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 3276/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 1.14 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 2244/BHM | 07/07/2023 | 07/07/2023 | Resource Division | 2.09 | 0 | 0 | 0
5 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Supply and delivery and installation of MCC panel at NOHANA PWSS (Mathpalsa) in Sainthia block under Bolpur Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001379/2023-2024 | 561/BOL.MD | 15/03/2024 | 11/09/2024 | BIRBHUM ELECTRIC WORKS | 8.74 | 8.72 | 99.71 | 100
6 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Providing FHTC and laying of pipe line for the villages rest portion of Rongaipur & Mathpalsa & all other allied works under Augmentation of Mathpalsa Piped Water Supply Scheme, Sainthia Block under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000146/2024-2025 | 2516/BHM | 04/09/2024 | 02/09/2025 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 35.86 | 0 | 0 | 70
7 | BIRBHUM |  | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Balance work for laying of pipe line including FHTC for augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. . | AE | JE1 | ORD/000132/2023-2024 | 2075/BHM | 08/06/2023 | 30/01/2025 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 45.68 | 40.01 | 87.58 | 100
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Mathpalsa Piped Water Supply Scheme | SM/10315 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Mathpalsa water supply scheme (P.H. No.-III) under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000006/2023-2024 | 715/Bol.MD | 19/04/2023 | 03/06/2023 | BIRBHUM ELECTRIC WORKS | 12.72 | 7.74 | 60.87 | 60
Total | [13 empty] | 253.75 | 197.62 | 77.88