## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system including functional household for proposed augmentation scheme for Murarai Piped Water Supply Scheme under Murarai ¿ I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE | JE1 | ORD/000004/2022-2023 | 555/BHM | 08/04/2022 | 05/10/2022 | SK ALIM | 392.31 | 229.36 | 58.46 | 72
2 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Repairing & renovation of Boundary Wall with Land filling at Head Work site (Murarai-1 Dev. Block) at Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000013/2022-2023 | 199/AE/NSD | 01/04/2022 | 01/05/2022 | M/S S.N CONSTRUCTION | 4.85 | 4.82 | 99.48 | 100
3 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Functional Household Tap Connection(FHTC) from existing distribution system in Rudranagar Pathanpara (Chatra Zone-II) W/S Scheme (Rudranagar) under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte. (Sl. No.10) | AE | JE | ORD/000090/2022-2023 | 139/BH | 15/06/2022 | 05/07/2022 | ISLAM CONSTRUCTION | 4.75 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Renovation of Boundary Wall near Switch Room at Rajgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (2nd Call) | AE | JE2 | ORD/000190/2022-2023 | 394/AE/NSD | 18/08/2022 | 17/10/2022 | MD ASIF ALI | 4.85 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Repairng, Renovation of Pump house & repairing of CWR of Murarai Piped Water Supply Scheme at RWS,Birbhum Sub-Division under Birbhum Division, PHE Dte.(Sl. No.01) | AE |  | ORD/000063/2022-2023 | 86/BH | 05/05/2022 | 25/05/2022 | M/S S.N CONSTRUCTION | 4.77 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | AE | JE2 | ORD/000275/2022-2023 | 805 /BHM | 12/04/2022 | 09/10/2022 | MANASH GHOSH | 397.16 | 13.66 | 3.44 | 100
7 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Rajgram (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000490/2021-2022 | 65/AE/NSD | 11/02/2022 | 26/02/2022 | MOYTEC | 0.99 | 0.99 | 100 | 100
8 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Chatra Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000491/2021-2022 | 66/AE/NSD | 11/02/2022 | 26/02/2022 | MOYTEC | 0.99 | 0.99 | 100 | 100
9 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Kaytha Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000492/2021-2022 | 67/AE/NSD | 11/02/2022 | 26/02/2022 | MOYTEC | 0.99 | 0.99 | 100 | 100
10 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000493/2021-2022 | 68/AE/NSD | 11/02/2022 | 26/02/2022 | G.MITRA & ASSOCIATE | 0.98 | 0.98 | 100 | 100
11 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000494/2021-2022 | 69/AE/NSD | 11/02/2022 | 26/02/2022 | GEOCON INDIA | 0.99 | 0.99 | 100 | 100
12 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Surging of 2 nos. existing Tube wells of Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000555/2021-2022 | 695/AE/NSD | 31/12/2021 | 15/01/2022 | GOLAM RASUL | 0.63 | 0.63 | 100 | 100
13 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000574/2021-2022 | 691/AE/NSD | 30/12/2021 | 14/01/2022 | G.MITRA & ASSOCIATE | 0.99 | 0.99 | 100 | 100
14 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000634/2021-2022 | 592/AE/NSD | 23/11/2021 | 07/01/2022 | MD ASIF ALI | 4.82 | 4.72 | 97.83 | 50
15 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply & delivery of sluice valve for Augmentation of Rajgram W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE(HQ) |  | ORD/000806/2021-2022 | 561/BHM | 15/03/2022 | 30/03/2022 | SSPR VALVE MANUFACTURING PVT LTD | 0.97 | 0.97 | 100 | 100
16 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Repairing of Pump House of Bara Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | AE |  | ORD/000774/2021-2022 | 35/BH | 09/03/2022 | 08/04/2022 | RANJIT GHOSH | 0.86 | 0 | 0 | 0
17 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying of 160mm dia. HDPE pipe line from CWR site to Dhabuni village, of Laxshminarayan Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. (2nd Call)¿(Sl. No.9) | AE | JE1 | ORD/000617/2020-2021 | 1708/BHM | 07/10/2020 | 21/11/2020 | HUMAYUN KABIR | 39.25 | 39.25 | 99.99 | 100
18 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Lohapur PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | AE | JE2 | ORD/000103/2022-2023 | 354/AE/NSD | 20/07/2022 | 18/09/2022 | GOLAM RASUL | 4.84 | 4.84 | 99.97 | 100
19 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm 50 m. deep (Replacement No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Laxminarayanpur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000892/2021-2022 | 124/AE/NSD | 04/03/2022 | 03/04/2022 | BELAL SK | 3.3 | 2.82 | 85.56 | 98
20 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Lohapur Water Supply Scheme at New Head Work site under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000109/2022-2023 | 362/AE/NSD | 21/07/2022 | 04/09/2022 | HARUN AR RASHID | 4.83 | 4.34 | 89.77 | 99
21 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000849/2021-2022 | 120/AE/NSD | 03/03/2022 | 02/04/2022 | DATA CONSTRUCTION | 4.8 | 4.37 | 91.02 | 100
22 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Murarai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000888/2021-2022 | 125/AE/NSD | 04/03/2022 | 03/04/2022 | NUR MOBINUL ISLAM | 4.79 | 3.54 | 73.77 | 100
23 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr. x 3.6 mtr. size with sanitary and water supply arrangement at Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE2 | ORD/000098/2022-2023 | 351/AE/NSD | 19/07/2022 | 17/09/2022 | NUR MOBINUL ISLAM | 4.99 | 4.98 | 99.8 | 100
24 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Restoration of concrete road including dismantling of concrete at Node point 26,27,28,97 & 99 for Augmentation of Murarai and its adjoining mouzas Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000183/2022-2023 | 344/AE/NSD | 18/07/2022 | 17/08/2022 | SK ABDUL HALIM | 4.97 | 4.95 | 99.74 | 100
25 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Re-Construction of damaged Boundary Wall at 1 no. Tube well site of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000212/2022-2023 | 407/AE/NSD | 05/09/2022 | 20/10/2022 | GOLAM RASUL | 4.99 | 4.98 | 99.95 | 100
26 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply & delivery of Sluice Valve for augmentation of Bhadrapur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) | AE(HQ) |  | ORD/000129/2022-2023 | 1242/BHM | 03/06/2022 | 18/06/2022 | APORUPA CONSTRUCTION | 4.99 | 4.99 | 100 | 100
27 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply & delivery of Sluice Valve for augmentation of Rajgram W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-01) | AE(HQ) |  | ORD/000131/2022-2023 | 1241/BHM | 03/06/2022 | 18/06/2022 | SSPR VALVE MANUFACTURING PVT LTD | 4.99 | 4.99 | 100 | 100
28 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Collection Household details including Geo reference in habitations named Jagannathpur, Sonarpur, Natun Abdullahapur, Puratan Abdullahapur & Vatra under Rajgram Water Supply Scheme under Nalhati Sub-Division, P.H.E. Dte. | AE | JE2 | ORD/000903/2021-2022 | 311/AE/NSD | 29/05/2021 | 13/06/2021 | MD ASIF ALI | 0.32 | 0.18 | 56.8 | 72
29 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying of Distribution pipeline through road crossing by adopting Jack Pushing method near Natun Bazar more to Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000181/2022-2023 | 405/AE/NSD | 05/09/2022 | 05/10/2022 | M/S PROCHESTA ENTERPRISE | 4.97 | 4.89 | 98.33 | 100
30 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000185/2022-2023 | 389/AE/NSD | 16/08/2022 | 15/10/2022 | NUR MOBINUL ISLAM | 4.83 | 3.9 | 80.73 | 97
31 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Kaitha PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE2 | ORD/000847/2021-2022 | 636/AE/NSD | 03/12/2021 | 17/01/2022 | ENAMUL ISLAM | 4.79 | 4.04 | 84.31 | 96
32 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of RCC Retaining Wall including Land filling towards approach of Pump House at Head Work site of Bara Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000216/2022-2023 | 412/AE/NSD | 08/09/2022 | 23/10/2022 | DATA CONSTRUCTION | 4.99 | 4.98 | 99.8 | 100
33 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Murarai PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | AE | JE1 | ORD/000102/2022-2023 | 353/AE/NSD | 20/07/2022 | 18/09/2022 | M/S S.N CONSTRUCTION | 4.84 | 4.78 | 98.74 | 100
34 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply & Installation of Submersible Pumping machinery at newly sunk Tubewell & others allied works at Kaitha Augmentation water supply scheme under Bolpur Mechanical Division P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000230/2022-2023 | 570/AE-III | 10/05/2022 | 30/05/2022 | WEST BENGAL ENGINEERING CO. | 2.35 | 2.33 | 99.13 | 0
35 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Bara (Zone-I) Water Supply Scheme at New Head Work site (Tube well-2) under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl No - 06) | AE | JE2 | ORD/000320/2022-2023 | 440/NSD | 19/09/2022 | 03/11/2022 | KAZI ZAKIR HOSSAIN | 4.82 | 4.41 | 91.5 | 0
36 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000285/2022-2023 | 485/AE/NSD | 20/10/2022 | 19/12/2022 | GOLAM RASUL | 4.84 | 4.28 | 88.4 | 100
37 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Replacement of existing pipeline by UPVC in Chatra Zone-I Water Supply Scheme under Nalhati Sub-Division under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000980/2021-2022 | 371/AE/NSD | 23/07/2021 | 06/09/2021 | ISLAM CONSTRUCTION | 4.84 | 4.46 | 92.2 | 100
38 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Repairing and renovation of boundary wall near OHR site at Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000794/2021-2022 | 447/AE/NSD | 26/08/2021 | 10/10/2021 | SHIB GANGA CONSTRUCTION | 4.84 | 4.82 | 99.53 | 100
39 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | electric quotation bill for Aug of Bhadrapur |  |  | VCH/000453/2022-2023 | BP/2022-23-09 | 02/06/2022 | 02/06/2022 | WBSEDCL | 1.39 | 0 | 0 | 0
40 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL quotation for Lohapur PWSS WS SCHEME under BOL MD PHE DTE |  |  | VCH/001159/2022-2023 | BP-2022-23-63 | 03/11/2022 | 03/11/2022 | WBSEDCL | 4.94 | 0 | 0 | 0
41 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Materials Payment |  |  | VCH/001322/2021-2022 | BP-2021-22-355 | 14/03/2022 | 14/03/2022 | RESOURCES DIVISION | 1265.56 | 0 | 0 | 0
42 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION BILL FOR Bara WS SCHEME |  |  | VCH/000576/2022-2023 |  | 18/07/2022 | 18/07/2022 | WBSEDCL | 4.02 | 0 | 0 | 0
43 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME |  |  | VCH/000804/2022-2023 | BP-2022-23-53 | 20/09/2022 | 20/09/2022 | WBSEDCL | 2.52 | 0 | 0 | 0
44 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME |  |  | VCH/000805/2022-2023 | BP-2022-23-54 | 20/09/2022 | 20/09/2022 | WBSEDCL | 1.35 | 0 | 0 | 0
45 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL Quotation bill for Bara ws scheme |  |  | VCH/000573/2022-2023 | BP-2022-23-21 | 04/08/2022 | 04/08/2022 | WBSEDCL | 4.02 | 0 | 0 | 0
46 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL Quoation bill for Rajgram W/S Scheme |  |  | VCH/000446/2022-2023 | BP-2022-23-01 | 01/06/2022 | 01/06/2022 | WBSEDCL | 10.48 | 0 | 0 | 0
47 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL Quoation bill for Rajgram W/S Scheme |  |  | VCH/000445/2022-2023 | BP-2022-23-03 | 01/06/2022 | 01/06/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
48 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Laxminarayanpur Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call). (Sl. No.14) | AE | JE1 | ORD/000635/2021-2022 | 562/BHM | 09/03/2022 | 08/05/2022 | BELAL SK | 76.15 | 75.9 | 99.68 | 100
49 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system including functional household for proposed augmentation scheme for Murarai Piped Water Supply Scheme under Murarai ¿ I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE | JE1 | ORD/000824/2021-2022 | 555/BHM | 08/03/2022 | 04/09/2022 | SK ALIM | 392.31 | 151.92 | 38.72 | 42
50 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Distribution system relating to argumentation of Rajgram Zone-I Piped Water Supply Scheme under Murarai-I Block, District - Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE2 | ORD/000960/2021-2022 | 647/BHM | 25/03/2022 | 21/09/2022 | MANASH GHOSH | 309.72 | 308.51 | 99.61 | 100
51 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Extension by HDPE Pipeline for the left out villages for proposed Augmentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl. No.2) | AE | JE2 | ORD/000126/2022-2023 | 1934/BHM | 06/09/2022 | 05/11/2022 | M/S GOUTAM DAS | 160.74 | 159.95 | 99.51 | 100
52 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Murarai water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | Driller in Charge | Junior Engineer | ORD/000301/2022-2023 | 964/Bol.MD | 13/10/2022 | 12/12/2022 | S.K.ELECTRICALS | 20.95 | 19.72 | 94.13 | 60
53 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | Assistant Engineer-III | Junior Engineer | ORD/000532/2022-2023 | 104/Bol.MD | 07/02/2023 | 09/03/2023 | M/S A.D.ENTERPRISE | 9.82 | 7.84 | 79.88 | 91
54 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing electro-mechanical accessories and others for Augmentation of Murarai water supply scheme T.W. No.-II, under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | Driller in Charge | Junior Engineer | ORD/000531/2022-2023 | 103/Bol.M.D | 07/02/2023 | 09/03/2023 | M/S SANTI CONSTRUCTION | 12.93 | 10.62 | 82.12 | 95
55 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied works for extension of HDPE pipe line including FHTC of Bhadrapur (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. |  | JE1 | ORD/000603/2022-2023 | 1047/BHM | 31/03/2023 | 30/05/2023 | M/S GOUTAM DAS | 96.04 | 61.29 | 63.82 | 0
56 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Bara Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000754/2022-2023 | 428/AE-III | 22/03/2023 | 11/04/2023 | MASSK ENGINEERING WORKS | 3.48 | 0 | 0 | 0
57 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of Voltage Correction device & other allied work for Augmentation of Laxminarayanpur water supply scheme under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000004/2023-2024 | 713/Bol.MD | 19/04/2023 | 03/06/2023 | QUAZI NOZRUL ISLAM | 14.45 | 14.45 | 100 | 0
58 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF MURARAI WATER SUPPLY SCHEME.UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | Driller in Charge | Junior Engineer | ORD/000060/2023-2024 | 778/AE-III | 27/06/2023 | 27/09/2023 | S. K. ENTERPRISE | 0.75 | 0 | 0 | 0
59 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Operation and Guarding of Pumping Machinery and others at Augmentation of Bhadrapur Zone-I Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000883/2022-2023 | 415/AE-III | 21/03/2023 | 20/06/2023 | M/S A.D.ENTERPRISE | 0.74 | 0 | 0 | 0
60 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF BARA Zone-I WATER SUPPLY SCHEME UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | Assistant Engineer-III | Junior Engineer | ORD/000022/2023-2024 | 653/AE-III | 26/04/2023 | 26/06/2023 | SINHA ELECTRICALS | 0.5 | 0 | 0 | 0
61 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply, delivery and installation of flow meter at for Augmentation of Laxminarayanpur water Supply under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000403/2023-2024 | 1043/AE-III | 07/08/2023 | 22/08/2023 | QUAZI NOZRUL ISLAM | 2.65 | 0 | 0 | 0
62 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Repairing of pump foundation and allied works at pump House under Augmentation of Bara piped water supply scheme.(Block Nalhati-II) under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000533/2023-2024 | 1076/AE-III | 21/08/2023 | 31/08/2023 | SINHA ELECTRICALS | 0.28 | 0 | 0 | 0
63 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia. 87 mtr. deep Tube well by rotary rig method using UPVC deep well screen (RDS) pipes with Ribs 200 mm dia. At Chatra Zone-II Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000245/2021-2022 | 444/AE/NSD | 26/08/2021 | 25/10/2021 | ISLAM CONSTRUCTION | 4.79 | 3.45 | 71.93 | 100
64 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000311/2021-2022 | 532/AE/NSD | 08/10/2021 | 22/11/2021 | SHIB GANGA CONSTRUCTION | 4.74 | 4.74 | 99.82 | 100
65 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte | AE | JE1 | ORD/000283/2021-2022 | 507/AE/NSD | 01/10/2021 | 15/11/2021 | SHIB GANGA CONSTRUCTION | 4.67 | 4.66 | 99.82 | 100
66 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near OHR side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE2 | ORD/000374/2021-2022 | 634/AE/NSD | 03/12/2021 | 17/01/2022 | MD. SHAHA JAMAL | 4.79 | 3.48 | 72.59 | 50
67 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near river side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE2 | ORD/000375/2021-2022 | 635/AE/NSD | 03/12/2021 | 17/01/2022 | GOLAM RASUL | 4.79 | 3.49 | 72.79 | 100
68 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-II PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE1 | ORD/000373/2021-2022 | 633/AE/NSD | 03/12/2021 | 17/01/2022 | RAJA CONSTRUCTION | 4.79 | 3.86 | 80.61 | 100
69 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Renovation of Boundary wall at Head Work Site (West Side) at Paikar Water Supply Scheme under Nalhati Sub Division within Birbhum Division Phe.Dte. | AE | JE1 | ORD/000171/2022-2023 | 348/AE/NSD | 19/07/2022 | 02/09/2022 | BISWAJIT RABIDAS | 3.09 | 3.04 | 98.45 | 0
70 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Rajgram water supply scheme under Bolpur Mechanical Division PHE Dte | Driller in Charge | Junior Engineer | ORD/000022/2022-2023 | 421/Bol.M.D | 12/05/2022 | 26/06/2022 | QUAZI NOZRUL ISLAM | 18.29 | 18.08 | 98.83 | 0
71 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bara Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000226/2022-2023 | 856/Bol.MD | 15/09/2022 | 14/11/2022 | SINHA ELECTRICALS | 21.35 | 20.2 | 94.62 | 100
72 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | AE | JE2 | ORD/000211/2022-2023 | 805/BHM | 12/04/2022 | 09/10/2022 | MANASH GHOSH | 397.16 | 381.86 | 96.15 | 100
73 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House at Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000379/2022-2023 | 570/NSD | 19/12/2022 | 02/02/2023 | GOLAM RASUL | 0.97 | 0.97 | 99.93 | 100
74 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Kaytha piped water supply scheme nalhati-I Block under Birbhum Division PHE Dte. (2nd Call) (Sl.No1) | AE | JE2 | ORD/000344/2022-2023 | 1159/BHM | 23/05/2022 | 31/03/2023 | PRANAB KUMAR GHOSH | 278.72 | 278.53 | 99.93 | 95
75 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House near new Head Work site at Augmentation of Murarai Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE1 | ORD/000381/2022-2023 | 572/NSD | 19/12/2022 | 02/02/2023 | NUR MOBINUL ISLAM | 0.97 | 0.67 | 69.18 | 100
76 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Chatra Piped Water Supply Scheme under Murarai ? I Block, under Birbhum Division, PHE Dte.?(Sl. No.3) | AE | JE2 | ORD/000263/2022-2023 | 957/BHM | 28/04/2022 | 25/10/2022 | M/S GOUTAM DAS | 427.38 | 427.32 | 99.99 | 100
77 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000302/2022-2023 | 965/Bol.MD | 13/10/2022 | 12/12/2022 | RAJIB COMPANY | 21.92 | 20.7 | 94.45 | 80
78 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Rajgram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (2nd Call) (Sl No-1) | AE | JE3 | ORD/000533/2022-2023 | 666//BHM | 28/02/2023 | 30/03/2023 | AMRT INDUSTRIES PRIVATE LIMITED | 8.42 | 8.42 | 100 | 100
79 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lohapur water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | Driller in Charge | Junior Engineer | ORD/000533/2022-2023 | 105/Bol.M.D | 07/02/2023 | 08/04/2023 | SHIVAM ENTERPRISE | 21.47 | 20.26 | 94.39 | 100
80 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Emergent repairing & relaying of 150 mm dia. DI Rising main of Laxminarayanpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000616/2022-2023 | 132/NSD | 31/03/2023 | 30/04/2023 | HUMAYUN KABIR | 0.96 | 0.69 | 71.87 | 100
81 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2021-2022 | 559/BHM | 08/03/2022 | 08/03/2022 | Resource Division | 1638.42 | 0 | 0 | 0
82 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 2291/BHM | 20/10/2022 | 20/10/2022 | Resource Division | 187.32 | 0 | 0 | 0
83 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2295/BHM | 20/10/2022 | 20/10/2022 | Resource Division | 15.26 | 0 | 0 | 0
84 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 2289/BHM | 20/10/2022 | 20/10/2022 | Resource Division | 115.36 | 0 | 0 | 0
85 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2207/BHM | 12/10/2022 | 12/10/2022 | Resource Division | 251.49 | 0 | 0 | 0
86 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1121/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 32.67 | 0 | 0 | 0
87 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 817/BHM | 15/03/2023 | 15/03/2023 | Resource Division | 36.51 | 0 | 0 | 0
88 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 2070/BHM | 14/06/2023 | 14/06/2023 | Resource Division | 36.96 | 0 | 0 | 0
89 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 945/BHM | 24/03/2023 | 24/03/2023 | Resource Division | 157.64 | 0 | 0 | 0
90 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 2278/BHM | 13/07/2023 | 13/07/2023 | Resource Division | 118.06 | 0 | 0 | 0
91 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 3575/ BHM | 18/08/2023 | 18/08/2023 | Resource Division | 1.91 | 0 | 0 | 0
92 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | ELECTRIC QUOTATION BILL FOR BARA WS SCHEME |  |  | BILL/00009/2023-2024 | BP-2023-2024-07 | 13/04/2023 | 13/04/2023 | WBSEDCL | 1.8 | 0 | 0 | 0
93 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sarda Bujung road from 0.00 km to 3.20 km under Birbhum Highway Division-I in the District of Birbhum Restoration work of hard shoulder portion with Jhama metal consolidation and moorum damaged by the PHE Dte. |  |  | BILL/00107/2023-2024 | BP-2023-24-64 | 08/06/2023 | 08/06/2023 | SAMSHER HOSSAIN | 5.16 | 0 | 0 | 0
94 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Lohapur Gumani setu with a link to lohapur railway station from 0.00 kmp and from 2.00 kmp to 6.40km under Birbhum Highway Division-I in the district of Birbhum Restoration of Widening. |  |  | BILL/00090/2023-2024 | BP-2023-24-61 | 07/06/2023 | 07/06/2023 | NATIONAL CONSTRUCTION | 9.65 | 0 | 0 | 0
95 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | wbsedcl quotation for amdol ws scheme |  |  | BILL/00710/2023-2024 |  | 28/07/2023 | 28/07/2023 | WBSEDCL | 3.65 | 0 | 0 | 0
96 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 1000 Cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for Augmentation of Lohapur Water Supply Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing). | AE | JE2 | ORD/000239/2022-2023 | 2203/BHM | 12/10/2022 | 21/10/2022 | SUNIL RABI DAS | 200.79 | 160.63 | 80 | 40
97 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied work for Extension of Pipe line including FHTC Work along with restoration of PWD & Other Connecting roads for Augmentation of Chatra Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (Sl. No.2) | AE | JE2 | ORD/000409/2022-2023 | 46/BHM | 04/01/2023 | 19/11/2025 | M/S GOUTAM DAS | 222.76 | 90.69 | 40.71 | 61
98 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 700 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Chatra W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing |  | JE2 | ORD/000046/2023-2024 | 1289/BHM | 18/04/2023 | 18/01/2024 | RAJGRAM FAV CO OPT LAB CON AND CONST SO LTD | 152.19 | 148.39 | 97.5 | 82
99 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and Installation of open well submersible Pumping machinery at existing CWR for Augmentation of Lakshminarayanpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000358/2023-2024 | 1006/AE-III | 25/07/2023 | 09/08/2023 | QUAZI NOZRUL ISLAM | 1.63 | 1.29 | 79.34 | 100
100 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 400 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Bara Zone II W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE2 | ORD/000267/2023-2024 | 3521/BHM | 11/08/2023 | 12/01/2025 | NABIN DEBNATH | 99.99 | 79.99 | 80 | 80
101 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000496/2021-2022 | 71/AE/NSD | 11/02/2022 | 26/02/2022 | GEOCON INDIA | 0.99 | 0.99 | 100 | 0
102 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Distribution system Relating to argumentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati - I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-1) | AE | JE1,JE2 | ORD/000711/2021-2022 | 548/BHM | 07/03/2022 | 02/11/2022 | M/S GOUTAM DAS | 505.15 | 183.04 | 36.24 | 100
103 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 1000 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying of HDPE pipeline from node point 6 to 13 and node point 272 to 378 and cutting & restoration of concrete road for laying of extension pipeline including FHTC for Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000284/2022-2023 | 2277/BHM | 19/10/2022 | 19/10/2023 | SK ALIM | 720.71 | 720.69 | 100 | 100
104 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bhadrapur Zone-I W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing)¿ (Sl. No.1) | AE | JE1 | ORD/000236/2022-2023 | 2467/BHM | 11/11/2022 | 11/08/2023 | M/S. JAN MAHAMMAD | 185.25 | 185.25 | 100 | 100
105 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House at Bara Zone-I Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000378/2022-2023 | 569/NSD | 19/12/2022 | 03/05/2023 | DATA CONSTRUCTION | 0.97 | 0.65 | 67.52 | 100
106 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Lohapur water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000767/2022-2023 | 426/AE-III | 22/03/2023 | 11/04/2023 | SUNIL RABIDAS | 4.34 | 2.28 | 52.46 | 100
107 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Emergent repair and replacement of Pipeline below the Railway culvert near Murarai Railway Station with allied works including extension of Pipe line of Murarai Aug. w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000102/2023-2024 | 1723/BHM | 12/05/2023 | 26/06/2023 | SK ALIM | 20.14 | 20.13 | 99.93 | 100
108 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied for balance work of distribution pipeline for Dhitora (Part) village including FHTC under Augmentation of Murarai W/S Scheme under Nalhati Sub-division within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000101/2023-2024 | 1722/BHM | 12/05/2023 | 11/06/2023 | M/S PROCHESTA ENTERPRISE | 35.04 | 34.86 | 99.5 | 100
109 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 550 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Kaytha W/S Scheme under Na Division hati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing |  | JE2 | ORD/000017/2023-2024 | 1183/BHM | 12/04/2023 | 12/01/2024 | S K CONSTRUCTION | 142.19 | 142.19 | 100 | 100
110 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and Allied for balance work of distribution pipeline including 315mm dia HDPE pipeline instead of 350mm dia DI pipeline along with restoration of roads and providing FHTC for Paikar w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte | AE | JE1 | ORD/000025/2023-2024 | 1100/BHM | 06/04/2023 | 01/01/2025 | SK ALIM | 455.72 | 336.68 | 73.88 | 100
111 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied work for Laying HDPE pipeline instead of DI Pipeline including Dismantling and restoration of Cement Concrete road for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. |  | JE2 | ORD/000124/2023-2024 | 1978/BHM | 05/06/2023 | 20/07/2023 | PASCON | 27.73 | 27.73 | 99.99 | 100
112 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Balance work for 160 mm dia HDPE Distribution main for Laksminarayanpur W/S Scheme, under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000130/2023-2024 | 1945/BHM | 01/06/2023 | 16/07/2023 | HUMAYUN KABIR | 37.63 | 37.48 | 99.6 | 100
113 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Lakshminaraynpur PWSS under Nalhati Sub- Division within Birbhum Division PHED. | AE | JE1,JE2 | ORD/000131/2023-2024 | 1947/BHM | 01/06/2023 | 16/07/2023 | A R ENTERPRISE | 7.95 | 4.88 | 61.4 | 100
114 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 1 no. new 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Rajgram PWSS at Jagannathpur CWR site under Nalhati Sub- Division within Birbhum Division PHED. | AE | JE2,JE3 | ORD/000128/2023-2024 | 2073/BHM | 08/06/2023 | 08/07/2023 | AJIMUL ISLAM | 6.7 | 5.54 | 82.65 | 100
115 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Bhadrapur Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE1 | ORD/000044/2022-2023 | 806/BHM | 12/04/2022 | 09/10/2022 | SUNIL RABI DAS | 407.95 | 400.74 | 98.23 | 100
116 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply delivery ,installation of MCC Panel and allied works at High Lift Site of Murarai water supply scheme [within Augmentation of Murarai Water Supply Scheme] under Bolpur Mechanical Division PHE Dte.. | Driller in Charge | Junior Engineer | ORD/000490/2023-2024 | 2251/BOL.MD. | 13/09/2023 | 12/11/2023 | M/S SAJAHAN CHOWDHURY | 11.4 | 11.32 | 99.28 | 100
117 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/000862/2023-2024 | 549/BMSD(D) | 24/11/2023 | 24/12/2023 | S.P. CONSTRUCTION | 2.97 | 2.79 | 93.83 | 100
118 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/000860/2023-2024 | 551/BMSD(D) | 24/11/2023 | 24/12/2023 | ABHISEK ENGTNEERING CONCERN | 2.05 | 1.87 | 91.08 | 100
119 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/000861/2023-2024 | 548/BMSD(D) | 24/11/2023 | 24/12/2023 | SARKAR ELECTRICAL | 2.05 | 1.85 | 89.91 | 100
120 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/000849/2023-2024 | 553/BMSD(D) | 24/11/2023 | 24/12/2023 | SINHA ELECTRICALS | 4.18 | 4.18 | 99.92 | 100
121 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/000882/2023-2024 | 552/BMSD(D) | 24/11/2023 | 24/12/2023 | UTTAM KUMAR CHATTERJEE | 2.33 | 2.17 | 93.13 | 100
122 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Erection of Cable on O.H pole and other allied works at Augmentation of Lohapur water supply scheme (T.W No- II) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001114/2023-2024 | 1657/AE-III | 22/12/2023 | 29/12/2023 | SUNIL RABIDAS | 0.68 | 0.68 | 100 | 100
123 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel and other allied works for Pump House No.III of Murarai Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/001090/2023-2024 | 018/BMSD(D) | 22/01/2024 | 21/02/2024 | QUAZI NOZRUL ISLAM | 2.44 | 2.4 | 98.5 | 100
124 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply, delivery and installation of servo motor operated copper wound line voltage corrector and other allied works at Pump House No.III of Murarai water supply scheme under Bolpur Mechanical Division, PHE Dte. | Driller in Charge | Junior Engineer | ORD/001098/2023-2024 | 019/BMSD(D) | 22/01/2024 | 21/02/2024 | M/S. UTTAM KUMAR CHATTERJEE | 3.62 | 3.6 | 99.51 | 100
125 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Replacement of power cable of distance pump of PH-I at Lohapur Water Supply Scheme (P.H.-I) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001229/2023-2024 | 510/BOL.MD | 13/03/2024 | 12/04/2024 | SINHA ELECTRICALS | 9.13 | 9.1 | 99.67 | 100
126 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and delivery of Kit kat fuse, Main switch, change over, Busbar switch for Augmentation of Murarai Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2024-2025 | 649/BMSD(D) | 02/09/2024 | 02/10/2024 | BIRBHUM ELECTRIC WORKS | 2.42 | 2.42 | 100 | 100
127 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and delivery of electro-mechanical accessories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000426/2024-2025 | 651/BMSD(D) | 02/09/2024 | 02/10/2024 | TAPAN ENTERPRISE | 1.89 | 1.89 | 100 | 100
128 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and delivery of Submersible pump motor set and accesssories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000427/2024-2025 | 662/BMSD(D) | 03/09/2024 | 03/10/2024 | M/S. UTTAM KUMAR CHATTERJEE | 2.16 | 2.16 | 100 | 100
129 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Kaytha water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000005/2024-2025 | 688./AE-III | 08/04/2024 | 29/04/2024 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.98 | 2.98 | 100 | 100
130 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | wbsedcl quotation for lohapur ws scheme |  |  | BILL/01873/2023-2024 | BP-23-24-278 | 29/02/2024 | 29/02/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
131 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Quotation deposit for empowering Sadashibpur Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00362/2024-2025 | BP-24-25-135 | 29/07/2024 | 29/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.51 | 0 | 0 | 0
132 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION FOR LOKEPUR DAS PARA SCHEME UNDER RAJGRAM WS SCHEME |  |  | BILL/02256/2023-2024 | BP-23-24-322 | 18/03/2024 | 18/03/2024 | WBSEDCL | 0.09 | 0 | 0 | 0
133 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION FOR KARULIA MINI SCHEME UNDER RAJGRAM WS SCHEME |  |  | BILL/02255/2023-2024 | BP-23-24-321 | 18/03/2024 | 18/03/2024 | WBSEDCL | 0.45 | 0 | 0 | 0
134 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | WBSEDCL QUOTATION FOR ASENGA PH NO I UNDER RAJGRAM WS SCHEME |  |  | BILL/02257/2023-2024 | BP-23-24-323 | 18/03/2024 | 18/03/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
135 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Quotation for new service connection at Kaitha PWSS (Block-Nalhati - I), Lohapur CCC, WBSEDCL |  |  | BILL/00218/2024-2025 | BP-24-25-100 | 02/07/2024 | 02/07/2024 | WBSEDCL | 6.71 | 0 | 0 | 0
136 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Additional Quotation deposit for empowering Augmentation of Rajgram Water Supply Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00221/2024-2025 | BP-24-25-99 | 02/07/2024 | 02/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.24 | 0 | 0 | 0
137 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Sinking of 200 mm dia 51.0 m deep Tube wells, Construction of Pump-House with retaining wall & inspection path including Land development and Laying of 250 mm dia HDPE rising main with interconnection of Rajgram w/s Scheme, under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | AE | JE2,JE3 | ORD/000042/2022-2023 | 1072/BHM | 13/05/2022 | 21/10/2022 | SUNIL RABI DAS | 108.04 | 98.47 | 91.14 | 100
138 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Laxminarayanpur Piped Water Supply Scheme under Nalhati-I Block, under Birbhum Division, PHE Dte.(Sl. No.3) | AE | JE1 | ORD/000135/2022-2023 | 803/BHM | 12/04/2022 | 13/10/2023 | PASCON | 297.86 | 254.09 | 85.31 | 100
139 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system including functional household connection for proposed augmentation scheme for BARA Zone-I Piped Water Supply Scheme under Nalhati-II Block under Birbhum Division, PHE Dte.? (Sl. No.2) | AE | JE2 | ORD/000136/2022-2023 | 860/BHM | 20/04/2022 | 28/10/2024 | PASCON | 392.49 | 374.9 | 95.52 | 80
140 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying of Rising main from existing OHR (Zone-I) to proposed OHR (Zone-II) of Rajgram for Augmentation of Rajgram (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2,JE3 | ORD/000255/2022-2023 | 457/NSD | 27/09/2022 | 25/04/2023 | S P CONSTRUCTION | 4.98 | 0 | 0 | 100
141 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Distribution system relating to argumentation of Rajgram Zone-I Piped Water Supply Scheme under Murarai-I Block, District - Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE3 | ORD/000988/2021-2022 | 647 /BHM | 25/03/2022 | 21/09/2022 | MANASH GHOSH | 309.72 | 1.21 | 0.39 | 100
142 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Lohapur piped water supply scheme Nalhati-II Block under Birbhum division, PHE Dte. (Sl. No.5) | AE | JE2 | ORD/000246/2022-2023 | 1151/ BHM | 23/05/2022 | 12/05/2024 | SUNIL RABI DAS | 408.25 | 295.52 | 72.39 | 89
143 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied work for Laying of Balance pipe line of different dia as per revised drawing including Jack pushing with restoration of road and pipe carrying stracture along with extension of pipe line and balance FHTC of Augmentation of Lohapur Water Supply Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte.(Sl. No.1) | AE | JE2 | ORD/000483/2022-2023 | 259/BHM | 30/01/2023 | 21/09/2024 | SUNIL RABI DAS | 325.53 | 302.1 | 92.8 | 93
144 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Withrawing, Lowering & Cable laying of Submersible Pumping machinery at Laxminarayanpur water supply scheme, under Bolpur Mechanical Division P.H.E. Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division. | Driller in Charge | Junior Engineer | ORD/000009/2023-2024 | 553/AE-III | 05/04/2023 | 25/04/2023 | MONI ELECTRICAL WORKS | 2.83 | 2.81 | 99.1 | 100
145 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied works for Laying of 315 mm dia. HDPE pipe line instead of 350 mm dia. D.I. pipe line along with laying of 90 mm dia. HDPE pipe line to the left-out habitations along with restoration of road including Jack Pushing/augor boring of Rajgram (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000024/2023-2024 | 1246/BHM | 17/04/2023 | 01/07/2025 | MANASH GHOSH | 177.06 | 138.63 | 78.3 | 96
146 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including raft foundation and Balance work of distribution pipeline including extension of pipeline along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | AE | JE1 | ORD/000029/2023-2024 | 1107/BHM | 10/04/2023 | 10/10/2024 | SUNIL RABI DAS | 229.46 | 176.75 | 77.03 | 100
147 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Construction of 400 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Bara Zone I W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing |  | JE2 | ORD/000020/2023-2024 | 1184/BHM | 12/04/2023 | 12/01/2024 | TAPAN KUMAR DATTA | 112 | 21.67 | 19.35 | 65
148 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of Paikar Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte | Driller in Charge | Junior Engineer | ORD/000491/2023-2024 | 2246/Bol.MD | 13/09/2023 | 06/04/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 32.14 | 18.5 | 57.58 | 70
149 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Distribution system relating to argumentation of Rajgram Zone-II Water Supply Scheme under Murarai-I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-3) | AE | JE2,JE3 | ORD/000633/2021-2022 | 550/BHM | 07/03/2022 | 02/03/2023 | S P CONSTRUCTION | 401.32 | 341.17 | 85.01 | 99
150 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied works for replacement of MS pipe line in place of DI pipe,including restortion of road of Augmentation of Rjgram Water Supply Scheme (Zone-II) under Nalhati Sub-Division within Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE2,JE3 | ORD/000354/2022-2023 | 2690/BHM | 06/12/2022 | 05/05/2023 | S P CONSTRUCTION | 195.67 | 143.47 | 73.32 | 91
151 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Paikar Piped Water Supply Scheme Mararai-II Block under Birbhum Division PHE Dte (Sl.No. 2) | AE | JE1 | ORD/000343/2022-2023 | 1456/BHM | 07/07/2022 | 01/03/2025 | SK ALIM | 663.22 | 548.85 | 82.76 | 80
152 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PMGSY road Flank & Other Connecting road including dismantling work with Augur Boring for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000050/2023-2024 | 1243/BHM | 17/04/2023 | 30/10/2024 | PASCON | 97.58 | 96.01 | 98.39 | 55
153 | BIRBHUM |  | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | SM/10319 | Augmentation | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PWD road Flank & Other Connecting road including dismantling work with jack pushing, Augur Boring for Augmentation of Bara Zone-II Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000033/2023-2024 | 1099/BHM | 06/04/2023 | 03/10/2023 | MANASH GHOSH | 199.45 | 183.16 | 91.83 | 95
Total | [13 empty] | 14457.84 | 8032.64 | 55.56