## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Repairing Renovation and up-gradation of Resting Room of Security Guard of Mayureswar Piped Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000777/2021-2022 | 36/BH | 09/03/2022 | 08/04/2022 | SUBHANKAR ROY | 3.61 | 0 | 0 | 100
2 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | SUPPLY DELIVERY & INSTALLATION OF ELECTRO MECHANICAL ACCESSORIES AND OTHER ALLIED WORKS AT BISHNUPUR WATER SUPPLY SCHEME. UNDER BOLPUR MECHANICAL DIVISION PHE DTE. | Assistant Engineer-III | Junior Engineer | ORD/000125/2022-2023 | 740/AE-III | 24/06/2022 | 14/07/2022 | SUNIL RABIDAS | 4.85 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | AE | JE3 | ORD/000065/2022-2023 | 87/BH | 05/05/2022 | 25/05/2022 | RIPAN CONSTRUCTION | 2.72 | 0 | 0 | 0
4 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply delivery & Installation of Voltage correction device at Bishnapur Augmentation water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000328/2022-2023 | 1150/AE-III | 24/11/2022 | 08/01/2023 | SUNIL RABIDAS | 3.37 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 1 No. 200 mm dia 72 Metre deep tubewell fitted with 200 mm dia PVC pipe and fibre glass stainer etc under Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000368/2021-2022 | 176/BH | 03/11/2021 | 18/11/2021 | AMIT KUMAR ROY | 3.5 | 0 | 0 | 82
6 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of one unmber 200mm dia 50m. deep tubewell fitted with 200mm dia. PVC pipe and Strainer etc. at Bishnupur W/S Scheme under RWS, Birbhum Sub-Division,PHE Dte. | AE | JE3 | ORD/000732/2021-2022 | 20/BH | 18/02/2022 | 10/03/2022 | TAPAN ENTERPRISE | 2.65 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Bishnupur W/S Scheme (Sl. No.-49) | AE | JE3 | ORD/000635/2020-2021 | 1865/BHM | 31/12/2020 | 31/12/2021 | TAPAN ENTERPRISE | 2.99 | 0 | 0 | 0
8 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur water supply scheme, Dist-Birbhum under Birbhum Division,PHE.Dte.(Part-II) | AE | JE3 | ORD/000829/2021-2022 | 22/BH | 18/02/2022 | 10/03/2022 | BHASKAR MANDAL | 2.02 | 0 | 0 | 92
9 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur W/S Scheme dist. birbhum division, PHE Dte.(Part-I) | AE | JE3 | ORD/000868/2021-2022 | 21/BH | 18/02/2022 | 10/03/2022 | TAPAN ENTERPRISE | 4.83 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Allied Work in connection with Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water Supply Scheme under RWS Birbhum Sub Division,within Birbhum Division PHEDte ,Suri, Birbhum..(Sl. No.04) | AE | JE3 | ORD/000089/2022-2023 | 133/BH | 15/06/2022 | 05/07/2022 | SAI BABA CONSTRUCTION | 0.94 | 0 | 0 | 100
11 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Distribution System within the command area of Bishnupur Water Supply Scheme (Baswa Latpara & Lalitakundu Purba Para) under RWS Birbhum Sub-Division, within Birbhum Division, PHE Dte.(Sl. No.06) | AE | JE3 | ORD/000080/2022-2023 | 135/BH | 15/06/2022 | 15/07/2022 | BIJOY KUMAR CHOUDHURY | 4.58 | 0 | 0 | 100
12 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water supply scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (sl. no.) | AE | JE3 | ORD/000886/2021-2022 | 56/BH | 17/03/2022 | 06/04/2022 | SAI BABA CONSTRUCTION | 1.07 | 0 | 0 | 100
13 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Repairing and Renovation of Bargachha Pump House and Boundary Wall under Md. Bazar Piped Water Supply Scheme under RWS, Birbhum Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000902/2021-2022 | 34/BH | 09/03/2022 | 08/04/2022 | ARYAN CONSTRUCTION | 3.9 | 0 | 0 | 100
14 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | AE | JE3 | ORD/000146/2022-2023 | 87/BH | 05/05/2022 | 25/05/2022 | RIPAN CONSTRUCTION | 2.73 | 0 | 0 | 0
15 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying of UPVC pipe line for supply of drinking water at Damra Namupara village under Md. Bazar Block within Birbhum Division, P.H. E Dte. (Sl. No. - 05) | AE | JE3 | ORD/000743/2020-2021 | 50/BSSD | 18/02/2021 | 05/03/2021 | B.M.SARKAR | 4.86 | 0 | 0 | 100
16 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Materials Payment |  |  | VCH/001324/2021-2022 | BP-2021-22-355 | 14/03/2022 | 14/03/2022 | RESOURCES DIVISION | 497.76 | 0 | 0 | 0
17 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | quotation for Aug. of Bishnupur water supply scheme |  |  | BILL/00091/2022-2023 | BP-2022-2023-79 | 20/12/2022 | 20/12/2022 | WBSEDCL | 1.98 | 0 | 0 | 0
18 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Repairing and Renovation of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under Birbhum Division, P.H.E. Dte.(Sl. No.05) | AE | JE3 | ORD/000062/2022-2023 | 89/BH | 05/05/2022 | 04/06/2022 | BHASKAR MANDAL | 4.05 | 0 | 0 | 100
19 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution System including providing Functional Household Tap Connection(FHTC) within the command area Augmentation of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.14) | AE | JE3 | ORD/000493/2022-2023 | 285/BHM | 01/02/2023 | 18/03/2023 | TAPAN KUMAR DATTA | 74.19 | 0 | 0 | 16
20 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE3 | ORD/000502/2022-2023 | 334/BHM | 02/02/2023 | 03/04/2023 | JAHIR HOSSAIN | 10.42 | 0 | 0 | 0
21 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply & delivery of Chlorination System at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000812/2022-2023 | 528/AE-III | 28/03/2023 | 17/04/2023 | M/S S.R. ENTERPRISE | 2.7 | 0 | 0 | 0
22 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply delivery & Installation of Voltage correction device at Mollarpur Zone-II (Kamraghat) water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000049/2023-2024 | 1036/Bol.MD | 05/06/2023 | 20/07/2023 | S.K.ELECTRICALS | 12.8 | 0 | 0 | 0
23 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Driller in Charge | Junior Engineer | ORD/000253/2023-2024 | 1437/Bol.MD | 11/07/2023 | 25/08/2023 | TAPAN ENTERPRISE | 5.24 | 0 | 0 | 0
24 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000362/2023-2024 | 3994/BHM | 05/10/2023 | 04/12/2023 | ABDUL MOTALIB | 11.13 | 0 | 0 | 0
25 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000357/2023-2024 | 3955/BHM | 03/10/2023 | 03/04/2024 | AINUL SHAIKH | 9.98 | 0 | 0 | 0
26 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 01 Nos Tube well 200 mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000034/2022-2023 | 184/RSD | 02/05/2022 | 01/06/2022 | HARUN AR RASHID | 4.97 | 0 | 0 | 100
27 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | AE | JE3 | ORD/000088/2022-2023 | 138/BH | 15/06/2022 | 05/07/2022 | BIJOY KUMAR CHOUDHURY | 3.6 | 0 | 0 | 50
28 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution system including functional household connection for proposed Augmentation of Hatgacha Piped Water Supply Scheme in Md. Bazar Block under Birbhum Division, P.H.E Dte.¿ (Sl. No.1) | AE | JE3 | ORD/000041/2022-2023 | 1027/BHM | 12/05/2022 | 08/11/2022 | S S ENTERPRISE | 428.01 | 0 | 0 | 100
29 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | AE | JE3 | ORD/000081/2022-2023 | 136/BH | 15/06/2022 | 15/07/2022 | BIJOY KUMAR CHOUDHURY | 4.71 | 0 | 0 | 50
30 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.7) | AE | JE3 | ORD/000407/2022-2023 | 39/BHM | 04/01/2023 | 05/03/2023 | SK GOLAM MORTUJA | 11.37 | 0 | 0 | 100
31 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room cum chlorine room with sanitary and water supply arrangement 5.40mtr.x 3.65mtr. size Bishnupur W/S Scheme under Rumpurhat Sub- Division,P.H.E. Dte. | AE | JE3 | ORD/001087/2021-2022 | 23/BH | 18/02/2022 | 10/03/2022 | TAPAN ENTERPRISE | 4.98 | 0 | 0 | 100
32 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Alided work of Connecting pipe line from Ground Bore Tube Well to Existing distribution system of Bishnupur Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.2) | AE | JE | ORD/000476/2022-2023 | 226/BHM | 20/01/2023 | 04/02/2023 | SEVAK CO - OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD | 2.42 | 0 | 0 | 100
33 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 04 (Four) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augmentation of Mayureswar PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.1) (2nd Call) | AE | JE3 | ORD/000551/2022-2023 | 810/BHM | 14/03/2023 | 13/05/2023 | SATYAJIT GHOSH | 74.84 | 0 | 0 | 100
34 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 03 (Three) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augumentation of Mollarpur Zone-I PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.3) (2nd Call) | AE | JE1 | ORD/000539/2022-2023 | 713/BHM | 02/03/2023 | 16/04/2023 | SUNIL RABI DAS | 56.14 | 0 | 0 | 100
35 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Head work Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development for (PH No-1) for Augumentation of Mollarpur Zone-II Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE1 | ORD/000512/2022-2023 | 518/BHM | 20/02/2023 | 21/04/2023 | ANARUL HOQUE | 14.5 | 0 | 0 | 100
36 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply & delivery of Cable at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000802/2022-2023 | 519/AE-III | 28/03/2023 | 17/04/2023 | SATYAJIT GHOSH | 3.21 | 0 | 0 | 0
37 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply & delivery of Column pipe & others at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000801/2022-2023 | 515/AE-III | 28/03/2023 | 17/04/2023 | S.K.ELECTRICALS | 2.46 | 0 | 0 | 0
38 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Md. Bazar water supply scheme under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000010/2023-2024 | 718/Bol.MD | 19/04/2023 | 03/06/2023 | HINDOL ROY | 35.27 | 0 | 0 | 100
39 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Painting of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.8) | AE | JE | ORD/000479/2022-2023 | 229/BHM | 20/01/2023 | 04/02/2023 | BHASKAR MANDAL | 1.76 | 0 | 0 | 100
40 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying of bypass Connection line and Land Development at Khorasinpur Ohr site under Mollarpur Zone-II W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE3 | ORD/000390/2021-2022 | 371/RSD | 28/09/2021 | 28/10/2021 | SHIB GANGA CONSTRUCTION | 4.24 | 0 | 0 | 100
41 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2021-2022 | 596/BHM | 09/03/2022 | 09/03/2022 | Resource Division | 525.88 | 0 | 0 | 0
42 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 2208/BHM | 12/10/2022 | 12/10/2022 | Resource Division | 6.02 | 0 | 0 | 0
43 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 2294/BHM | 20/10/2022 | 20/10/2022 | Resource Division | 5.82 | 0 | 0 | 0
44 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 1123/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 32.67 | 0 | 0 | 0
45 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 2071/BHM | 14/06/2023 | 14/06/2023 | Resource Division | 30.8 | 0 | 0 | 0
46 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 2277/BHM | 13/07/2023 | 13/07/2023 | Resource Division | 54.13 | 0 | 0 | 0
47 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOATAION FOR MUYURESWAR WS SCHEME |  |  | BILL/00723/2023-2024 | BP-2023-2024-74 | 23/08/2023 | 23/08/2023 | WBSEDCL | 2.64 | 0 | 0 | 0
48 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOTATION FOR RAJCHANDRAPUR P.H.NO. 4 PWSS FOR AUG. OF MAYURESWAR WS SCHEME |  |  | BILL/01277/2023-2024 | BP-23-24-132 | 17/10/2023 | 17/10/2023 | WBSEDCL | 5.26 | 0 | 0 | 0
49 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOTATION FOR MAYURESWAR WS SCHEME |  |  | BILL/00724/2023-2024 | BP-2023-2024-75 | 24/08/2023 | 24/08/2023 | WBSEDCL | 4.48 | 0 | 0 | 0
50 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR |  |  | BILL/00932/2023-2024 | BP-2023-2024-80 | 18/09/2023 | 18/09/2023 | WBSEDCL | 2.99 | 0 | 0 | 0
51 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOATATION MONEY FOR MOLLARPUR ZONE-II WS SCHEME |  |  | BILL/00114/2023-2024 | BP-2023-2024-33 | 18/05/2023 | 18/05/2023 | WBSEDCL | 2.9 | 0 | 0 | 0
52 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR |  |  | BILL/00931/2023-2024 | BP-2023-2024-81 | 18/09/2023 | 18/09/2023 | WBSEDCL | 4.98 | 0 | 0 | 0
53 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Augmentation of Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000025/2022-2023 | 174/RSD | 29/04/2022 | 29/05/2022 | GEOCON INDIA | 0.99 | 0 | 0 | 100
54 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 03 (Three) nos. Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia for source Augmentation of Hatgacha PWSS under Rampurhat Sub-Division, Birbhum Division P.H.E Dte. | AE,AE(HQ) | JE1,JE2 | ORD/000357/2024-2025 | 3156/BHM | 19/11/2024 | 03/01/2025 | BHABATARAN SADHU | 9.87 | 0 | 0 | 0
55 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augmentation of Mayureswar Piped Water Supply Scheme, Block -Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.6) | AE | JE3 | ORD/000382/2022-2023 | 2842/BHM | 21/12/2022 | 19/02/2023 | NOBI SEIKH | 13.39 | 0 | 0 | 100
56 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road, Land Development (PH No-3) for Augmentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE3 | ORD/000391/2022-2023 | 2914/BHM | 27/12/2022 | 25/02/2023 | SAFIUDDIN SEKH | 11.25 | 0 | 0 | 100
57 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying of Balance Distribution Main pipeline through road crossing of SH 11 and Md Bazar-Kulkuri Road (Node R1-1, 4-47, 7-87, 9-108, 18-24, 28-29, 30-270 & 34-317) and NH-14 (Node 33-34) by adopting Jack Pushing method for Augmentation of Md Bazar Piped Water Supply Scheme under Md Bazar Block, under Birbhum Division P.H.E Dte. | AE(HQ) | JE3 | ORD/000602/2022-2023 | 1046/BHM | 31/03/2023 | 30/05/2023 | M/S GOUTAM DAS | 57.55 | 0 | 0 | 0
58 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Hatgacha Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte | AE | JE3 | ORD/000032/2023-2024 | 1097/BHM | 06/04/2023 | 05/07/2023 | S S ENTERPRISE | 273.65 | 0 | 0 | 50
59 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Allied work for balance portions of Laying distribution system for proposed augmentation scheme of Md.Bazar Piped Water Supply Scheme under Md.Bazar Block, Sinking of 200 mm dia. tubewell (03 nos.) 28 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer with connecting pipe line with surging of existing 2 (Two) nos. Tube well including renovation of boundary wall at Head Work Site of Md. Bazar Piped Water Supply Scheme under Birbhum Division PHE Dte. | AE(HQ) | Estimator | ORD/000118/2023-2024 | 2079/BHM | 08/06/2023 | 07/08/2023 | M/S GOUTAM DAS | 52.61 | 0 | 0 | 100
60 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 01 (One) No. Tube well 200 mm X 200 mm dia X180m. deep tube wells by Rotary Rig including connecting main at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000298/2023-2024 | 3673/BHM | 29/08/2023 | 13/10/2023 | HARUN AR RASHID | 13.71 | 0 | 0 | 100
61 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000351/2023-2024 | 3948/BHM | 03/10/2023 | 03/04/2024 | ABUL HASNATH | 11.59 | 0 | 0 | 100
62 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply & Delivery of power cable for Augmentation of Bishnupur (Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer-III | Junior Engineer | ORD/000710/2023-2024 | 1362/AE-III | 17/10/2023 | 01/11/2023 | M. S. ENTERPRISE | 4.32 | 0 | 0 | 100
63 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 2 Nos. 200 mm dia X 66 mtr. deep Tubewell with UPVC pipe and strainer for Bishnupur W/S Scheme under Birbhum Division, PHE Dte. | AE | JE | ORD/000450/2023-2024 | 09/BHM | 03/01/2024 | 30/08/2024 | HARUN AR RASHID | 8.38 | 0 | 0 | 97
64 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and delivery of kit kat fuse, Main switch, change over switch, bushbar for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000425/2024-2025 | 650/BMSD(D) | 02/09/2024 | 02/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.51 | 0 | 0 | 100
65 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional work for connecting pipeline from ground bore tubewell 03 nos. existing distribution system of Bishnupur pipe water supply scheme under RWS, Birbhum Sub-Division within Birbhum Divsion, PHE Dte.(Sl.No.1) | AE | JE | ORD/000373/2024-2025 | 184/RWS | 21/11/2024 | 06/12/2024 | BHASKAR MANDAL | 0.97 | 0 | 0 | 70
66 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional estimate for installation Augmentation Mollarpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001170/2023-2024 | 299/AE-III | 22/02/2024 | 29/02/2024 | SUNIL RABIDAS | 4.89 | 0 | 0 | 100
67 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Replacement of voltage correction device at Mollarpur zone-I(Ph-III) (at Block compound) water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Mollarpur W/S Scehem) | Assistant Engineer-III | Junior Engineer | ORD/001179/2023-2024 | 309/AE-III | 23/02/2024 | 09/03/2024 | BIRBHUM ELECTRIC WORKS | 2.97 | 0 | 0 | 100
68 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | PROVIDING ELECTRO MECHANICAL ACCESSORIES AND OTHERS FOR Augmentation of Hatgacha water supply scheme UNDER BOLPUR MECHANICAL DIVISION IN THE DISTRICT OF BIRBHUM. | Driller in Charge | Junior Engineer | ORD/001303/2023-2024 | 667/Bol.MD | 22/03/2024 | 21/04/2024 | HINDOL ROY | 22.96 | 0 | 0 | 100
69 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and delivery of Submersible pump motor set, Slluice valve,NRV for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2024-2025 | 659/BMSD/(D) | 02/09/2024 | 02/10/2024 | B. P. TRADING CORPORATION | 1.52 | 0 | 0 | 100
70 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Quotation for new connection at Augmentation Mollarpur PWSS (Malanchi), block- Mayureswar-I |  |  | BILL/00079/2024-2025 | BP-2024-2025-36 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0 | 0
71 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. |  |  | BILL/00414/2024-2025 | BP-24-25-130 | 29/07/2024 | 29/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
72 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Mollarpur Zone-II Piped Water Supply Scheme, Block-Mayureswar-I under Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1,JE3 | ORD/000060/2022-2023 | 1152/BHM | 23/05/2022 | 11/05/2024 | SUNIL RABI DAS | 401.72 | 0 | 0 | 100
73 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE1,JE3 | ORD/000390/2022-2023 | 2915/BHM | 27/12/2022 | 25/02/2023 | SAFIUDDIN SEKH | 11.31 | 0 | 0 | 100
74 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Mollarpur Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.5) | AE | JE1,JE3 | ORD/000238/2022-2023 | 2247/BHM | 17/10/2022 | 17/07/2023 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 185.79 | 0 | 0 | 85
75 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Mayureswar Piped water supply scheme under Mayureswar Block-II in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000256/2023-2024 | 1438/Bol.MD | 11/07/2023 | 01/01/2025 | M. S. ENTERPRISE | 34.9 | 0 | 0 | 100
76 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Mollarpur Zone-I (Part-A) Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | AE | JE1,JE3 | ORD/000173/2024-2025 | 2630/BHM | 12/09/2024 | 10/12/2025 | M/S GOUTAM DAS | 90.71 | 0 | 0 | 55
77 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 02 nos. (01 Additional + 01 Replaced) Tube well (200mm dia, all through 150 mt. Deep) along with Rising Main and Construction of 01 no. Pump House for Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000175/2024-2025 | 2729/BHM | 25/09/2024 | 24/06/2025 | SUNIL RABI DAS | 23.99 | 0 | 0 | 70
78 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional Laying distribution system at Kotasur and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000569/2024-2025 | 400/BHM | 06/02/2025 | 07/05/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 97.7 | 0 | 0 | 0
79 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) by Adopting Jack Pushing Technique for laying Additional distribution system and Laying of Rising Main under Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | AE | JE1,JE2,JE3 | ORD/000174/2024-2025 | 2730/BHM | 25/09/2024 | 15/12/2025 | SUNIL RABI DAS | 96 | 0 | 0 | 30
80 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Rising Main with 200mm dia DI pipe and Delivery main with 200mm dia HDPE pipe for OHR under Bishnupur Piped Supply Scheme of Birbhum RWS Sub-Division, Block- Rampurhat-II, P.H.E. Dte. within Birbhum Division PHE Dte. | AE | JE3 | ORD/000690/2024-2025 | 865/BHM | 26/03/2025 | 25/05/2025 | TAPAN KUMAR DATTA | 40.58 | 0 | 0 | 0
81 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Jack pushing & Augur boring along with extension of pipeline, restoration of Roads and all allied works for Mohammad Bazar piped Water Supply Scheme under Birbhum Division P.H.E. Dte. | AE(HQ) | Estimator,JE | ORD/000688/2024-2025 | 862/BHM | 26/03/2025 | 30/08/2025 | M/S GOUTAM DAS | 69.84 | 0 | 0 | 100
82 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000041/2025-2026 | 736/BOL.MD | 29/04/2025 | 13/06/2025 | TAPAN ENTERPRISE | 5.24 | 0 | 0 | 0
83 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional Laying distribution system at different mouzas, including the Functional Household Tap Connection under Augmentation of Mollarpur Zone I (Part-B & C) Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, P.H.E. Dte. | AE | JE2,JE3 | ORD/000040/2025-2026 | 1452/BHM | 19/05/2025 | 16/11/2025 | M/S GOUTAM DAS | 121.47 | 0 | 0 | 40
84 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 03 (Three) Nos Tubewell 200 mm X 200 mm dia X180m. deep tubewells by Rotary Rig including connecting rising main at Augmentation of Mollarpur Zone-I (Part-C) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000118/2025-2026 | 634/RSD | 15/07/2025 | 13/09/2025 | PULAK KUMAR PAL | 38.38 | 0 | 0 | 0
85 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 01 (One) No. replacement & 01 (One) new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-A) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000208/2025-2026 | 737/RSD | 20/08/2025 | 19/10/2025 | RAJ ASSOCIATES | 40.56 | 0 | 0 | 0
86 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Sinking of 02 (Two) Nos. new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-B) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000236/2025-2026 | 2206/BHM | 26/08/2025 | 24/11/2025 | RADHARANI ENTERPRISE | 51.13 | 0 | 0 | 0
87 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Additional Laying distribution system at Mayureswar, Kushtor and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000264/2025-2026 | 2360/BHM | 11/09/2025 | 10/12/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 130.05 | 0 | 0 | 0
88 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Different works such as Pump House, Boundary wall, Rising main, LDS, repairing works and allied works related to Augmentation of Bishnupur PWSS within Birbhum RWS Sub-Division, under Birbhum Division, PHE Dte. | AE | JE | ORD/000257/2025-2026 | 2197/BHM | 22/08/2025 | 20/11/2025 | SUBHANKAR ROY | 109.95 | 0 | 0 | 0
89 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Mayureswar Piped Water Supply Scheme, Mayureswar-II Block under Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE3 | ORD/000040/2022-2023 | 1010/BHM | 11/05/2022 | 06/04/2025 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 502.2 | 0 | 0 | 100
90 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Md. Bazar Piped Water Supply Scheme under Md. Bazar Block, under Birbhum Division, PHE Dte (Sl. No.7) | AE,AE(HQ) | Estimator,JE3 | ORD/000264/2022-2023 | 859/BHM | 20/04/2022 | 31/08/2023 | M/S GOUTAM DAS | 319.7 | 0 | 0 | 95
91 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bishnupur W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.7) | AE | JE | ORD/000240/2022-2023 | 2727/BHM | 08/12/2022 | 08/09/2023 | S K CONSTRUCTION | 165.71 | 0 | 0 | 100
92 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Mollarpur Zone-I Piped Water Supply Scheme, Mayureswar-I Block, under Birbhum Division, PHE Dte. (2nd Call)¿ (SL.No.1) | AE | JE3 | ORD/000272/2022-2023 | 2246/BHM | 17/10/2022 | 25/05/2025 | M/S GOUTAM DAS | 908.98 | 0 | 0 | 78
93 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.5) | AE | JE3 | ORD/000478/2022-2023 | 228/BHM | 20/01/2023 | 21/03/2023 | CHOWDHURY ENTERPRISE | 11.39 | 0 | 0 | 100
94 | BIRBHUM |  | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Miscellaneous works including painting, earthling, repairing of entrance gate etc at head work site at Kharasinpur of OHR, Boundary Wall etc of Mollarpur Zone-II at Mollarpur Zone -II PWSS under Rampurhat Sub Division P.H.E Dte. | AE | JE3 | ORD/000055/2023-2024 | 1254/BHM | 17/04/2023 | 01/06/2023 | MD SURAJ ALI | 3.15 | 0 | 0 | 100
95 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division | SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Mollarpur Zone-I and Zone-II Piped water supply scheme under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/000251/2023-2024 | 1436/Bol.MD | 11/07/2023 | 02/09/2024 | SUNIL RABIDAS | 47.6 | 0 | 0 | 100
Total | [13 empty] | 6016.82 | 0 | 0