## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 2556/BHM | 21/11/2022 |  | Resource Division | 288.93 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Trial Bore and Sinking of 200 mm dia. 2(Two) nos.tubewell 30m. (avg.) depth fitted with PVC pipes & fittings Schedule 80 (medium duty) and Fibre Glass Strainer on the river bank of Ajoy under Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, PHE Dte. (Sl. No. -01) | AE | JE1 | ORD/000408/2022-2023 | 73/BSSD | 02/05/2022 | 17/05/2022 | SK FAQHRUL AMIN | 3.8 | 2.89 | 76 | 100
3 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Laying of Distribution Pipe line from Dihipara Hanuman Mandir to Kendragaria Railway crossing under Khoyrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE2 | ORD/001086/2021-2022 | 398/BSSD | 10/12/2021 | 25/12/2021 | B.M.SARKAR | 4.99 | 4.97 | 99.7 | 100
4 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Replacement of rising main pipe line from AC Pipe line to DI K9 and concreting work in the premesis of CWR site and other allied works under Augmentation of Khayrasole Piped Water Supply Scheme (Zone-I) under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division PHE Dte.(Sl. No. -16) | AE | JE1 | ORD/000595/2022-2023 | 227/BSSD | 21/09/2022 | 11/10/2022 | HIRANMAY GHOSH | 4.88 | 4.73 | 96.8 | 0
5 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1118/BHM | 10/04/2023 |  | Resource Division | 13.35 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE | JE1 | ORD/000274/2022-2023 | 1157/BHM | 23/05/2022 | 19/11/2022 | M/S S.S. ENTERPRISE | 372.63 | 372.32 | 99.92 | 80
7 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-II Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte? (Sl. No.5) | AE | JE2 | ORD/000257/2022-2023 | 1149/BHM | 23/05/2022 | 19/11/2022 | TIRUPATI ENTERPRISES | 229.96 | 223.47 | 97.18 | 85
8 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Construction of PCC Pillar for laying of 250 mm dia. rising main pipe line over Hinglow River near Pansuili for Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000598/2022-2023 | 1043/BHM | 31/03/2023 | 30/04/2023 | HIRANMAY GHOSH | 4.55 | 4.46 | 98.08 | 100
9 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 900/BHM | 26/04/2022 |  | Resource Division | 9.93 | 0 | 0 | 0
10 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 2292/BHM | 20/10/2022 |  | Resource Division | 64.91 | 0 | 0 | 0
11 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Balance work for Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, P.H.E. Dte | AE | JE | ORD/000257/2023-2024 | 3440/BHM | 03/08/2023 | 01/11/2023 | ARABINDA GUPTA | 298.61 | 114.07 | 38.2 | 52
12 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone I W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE1 | ORD/000012/2023-2024 | 1255/BHM | 17/04/2023 | 12/01/2024 | M/S KRIPASINDHU GHOSH & CO. | 151.36 | 45.41 | 30 | 70
13 | BIRBHUM |  | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme | SM/10343 | Augmentation | Construction of 200cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone II W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE |  | ORD/000092/2023-2024 | 1646/BHM | 02/05/2023 | 27/01/2024 | U TURN CONSTRUCTION | 71.24 | 45.42 | 63.75 | 89
Total | [13 empty] | 1519.13 | 817.72 | 53.83