## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Replacement of UPVC pipe line & Inter connection of D.I. pipeline from new tube well to rising main at Guskira village of Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000213/2022-2023 | 408/AE/NSD | 06/09/2022 | 06/10/2022 | SUPRABHAT RABIDAS | 4.84 | 4.65 | 95.95 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE2 | ORD/000016/2022-2023 | 229/AE/NSD | 21/04/2022 | 05/06/2022 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000294/2021-2022 | 508/AE/NSD | 01/10/2021 | 15/11/2021 | SHIB GANGA CONSTRUCTION | 4.67 | 4.67 | 100 | 67
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000285/2021-2022 | 509/AE/NSD | 01/10/2021 | 15/11/2021 | SUPRABHAT RABIDAS | 4.66 | 4.66 | 99.95 | 33
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Replacement with Extension of 63 & 75 mm Dia. UPVC Pipe line in different habitations within Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. | AE | JE2 | ORD/000010/2022-2023 | 206/AE/NSD | 05/04/2022 | 20/05/2022 | SUPRABHAT RABIDAS | 4.22 | 4.22 | 100 | 50
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE2 | ORD/000141/2022-2023 | 383/AE/NSD | 10/08/2022 | 24/09/2022 | MD ZIAUL ISLAM | 3.34 | 3.33 | 99.62 | 50
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS (Zone-I) under Nalhati Sub Division P.H.E.D (Sl. No.12) | AE | JE3 | ORD/000398/2022-2023 | 28/BHM | 04/01/2023 | 18/02/2023 | SUBHRANIL DAS | 11.64 | 11.6 | 99.68 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Approaching path to Pump House along with Land Development at OHR site of Gopalpur PWSS (Zone-II) under Nalhati Sub-Division, PHED. | AE | JE3 | ORD/000615/2022-2023 | 131/NSD | 31/03/2023 | 30/04/2023 | SUPRABHAT RABIDAS | 0.97 | 0.97 | 99.64 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS( Zone-II)under Nalhati Sub Division P.H.E.D. (Sl. No.11) | AE | JE2 | ORD/000401/2022-2023 | 31/BHM | 04/01/2023 | 18/02/2023 | ISLAM CONSTRUCTION | 17.06 | 16.88 | 98.94 | 0
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in left out habitations , under Ramchandrapur & Kestara Village (J.L:-100) under Murarai - I Block, within the command area of Gopalpur Zone II W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000083/2021-2022 | 370/AE/NSD | 22/07/2021 | 05/09/2021 | SUPRABHAT RABIDAS | 4.97 | 0 | 0 | 50
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) | SM/10543 | Retrofitting | Extension of distribution pipe line including repairing of FHTC at Kestara and Ramchandrapur habitation of Gopalpur Zone-II Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE3 | ORD/000462/2024-2025 | 3607/BHM | 31/12/2024 | 28/03/2025 | MD ASIF ALI | 11.89 | 0 | 0 | 10
Total | [13 empty] | 71.6 | 50.97 | 71.18