## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | SM/10665 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2 | ORD/000317/2022-2023 | 2509/BHM | 17/11/2022 | 17/12/2022 | AMIT KUMAR ROY | 38.19 | 38 | 99.5 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | SM/10665 | Retrofitting | Extension of distribution pipe line near Nichupara Kabar Sthan, besides of Khokon House, near Imam Saheb and infornt of Gate of Park and all other allied works under Data Baba Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | AE | JE2 | ORD/000345/2022-2023 | 215/BSSD | 21/09/2022 | 06/10/2022 | AMIT KUMAR ROY | 2.98 | 2.97 | 99.71 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme | SM/10665 | Retrofitting | Balance work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000099/2023-2024 | 1720/BHM | 12/05/2023 | 11/06/2023 | ARPAN PANDIT | 22.34 | 15.57 | 69.71 | 100
Total | [13 empty] | 63.51 | 56.54 | 89.03