## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11900 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,AE(HQ) | JE,JE1,JUNIOR ENGINEER | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 27/02/2026 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 373.41 | 3.36 | 92
2 | BIRBHUM | Suri-I | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11900 | New | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 28.06.2024 to 26.12.2024) | AE | JE | ORD/000089/2024-2025 | 96/RWS | 27/06/2024 | 23/12/2024 | ADIL CONSTRUCTION | 0.85 | 2.32 | 273.42 | 0
3 | BIRBHUM | Suri-I | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11900 | New | Supply of one no. diesel driven car(diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS,Birbhum Sub-Division, PHE Dte.(Period from 27/12/2024 to 24/07/2025) | AE | JE | ORD/000453/2024-2025 | 204/RWS | 27/12/2024 | 25/07/2025 | ADIL CONSTRUCTION | 1 | 1.95 | 196.33 | 0
Total | [13 empty] | 11112.3 | 377.69 | 3.4