## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11936 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,AE(HQ) | JE,JE1,JUNIOR ENGINEER | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 27/02/2026 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 435.69 | 3.92 | 92
2 | BIRBHUM | Rajnagar | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/11936 | New | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Khoyrasole & Rajnagar Development Block having less than 100 Households under Birbhum Division PHE Dte. | AE(HQ) | Estimator,JE | ORD/000167/2025-2026 | 2085/BHM | 13/08/2025 | 11/11/2025 | SYED GOLAM ZILANI | 11.28 | 0 | 0 | 90
Total | [13 empty] | 11121.74 | 435.69 | 3.92