## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12074 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,AE(HQ) | JE,JE1,JUNIOR ENGINEER | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 27/02/2026 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 458.43 | 4.13 | 92
2 | BIRBHUM | Dubrajpur | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. | SM/12074 | New | Road restoration along with all allied works at Mini PWSS less than 100HH & Naoadangal PWSS at Naoadangal,Aroan, Belahari, Choti Gunsima, Ghoga, Kkhannagar, Khosnagar, Sekandarpur & Shib Rautara villages of Dubrajpur Block under Birbhum Division, P.H.E.Dte | AE | JE,JE3 | ORD/000173/2025-2026 | 2093/BHM | 14/08/2025 | 12/11/2025 | RUBAL CONSTRACTION | 36.78 | 0 | 0 | 10
Total | [13 empty] | 11147.24 | 458.43 | 4.11