## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Meherpur and Adjoining Mouzas PWSS | SM/12457 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 1417/BHM | 24/04/2023 |  | Resource Division | 21.84 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Meherpur and Adjoining Mouzas PWSS | SM/12457 | New | Providing Electro-mechanical accessories and others for Meherpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000422/2023-2024 | 2092/Bol.MD | 22/08/2023 | 21/10/2023 | A.S.ENTERPRISE | 28.01 | 8.91 | 31.81 | 60
3 | BIRBHUM | Sainthia | Birbhum Division | Meherpur and Adjoining Mouzas PWSS | SM/12457 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 200 CuM capacity O.H.R, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at MEHERPUR & its adjoining mouzas water supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte" | AE | JE | ORD/000130/2024-2025 | 2264/BHM | 14/08/2024 | 14/08/2025 | PRANAB KUMAR GHOSH | 327.36 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | Meherpur and Adjoining Mouzas PWSS | SM/12457 | New | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 2491/BHM | 03/09/2024 |  | Resource Division | 9.36 | 0 | 0 | 0
Total | [13 empty] | 386.57 | 8.91 | 2.3