## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1422/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 40.92 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Providing Electro-mechanical accessories and others for Paschim Naopara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000433/2023-2024 | 2095/Bol.MD | 22/08/2023 | 01/04/2025 | BIRBHUM ELECTRIC WORKS | 27.94 | 21.83 | 78.14 | 50
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | New service connection at Paschim Nowapara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02240/2023-2024 | BP-2023-24-320 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.62 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | New service connection at Paschim Nowapara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02182/2023-2024 | BP-2023-24-319 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.69 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | WBSEDCL QUOTATION FOR PASCHIM NOWAPARA PH NO-I |  |  | BILL/02236/2023-2024 |  | 14/03/2024 | 14/03/2024 | WBSEDCL | 5.62 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 28/09/2025 | B RAI CONSTRUCTION COMPANY | 1402.44 | 281.09 | 20.04 | 45
Total | [13 empty] | 1487.23 | 302.92 | 20.37