## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Bolpur Mechanical | Abhirampur and Adjoining Mouzas PWSS | SM/12536 | New | Providing Electro-mechanical accessories and others for Abhirampur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000439/2023-2024 | 2098/Bol.MD | 22/08/2023 | 21/10/2023 | MONI ELECTRICAL WORKS | 27.98 | 16.55 | 59.16 | 50
2 | BIRBHUM | Sainthia | Birbhum Division | Abhirampur and Adjoining Mouzas PWSS | SM/12536 | New | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1371/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 50.48 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Birbhum Division | Abhirampur and Adjoining Mouzas PWSS | SM/12536 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE,JE1 | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 23/07/2025 | ASHOK KUMAR GHOSH | 1446.74 | 113.08 | 7.82 | 55
Total | [13 empty] | 1525.2 | 129.63 | 8.5