## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1472/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 53.39 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Providing Electro-mechanical accessories and others for Bonha PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000940/2023-2024 | 3301/BOL.MD | 29/09/2023 | 01/05/2025 | QUAZI NOZRUL ISLAM | 28.83 | 22.78 | 79.02 | 60
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | WBSEDCL QUOTATION FOR BONHA P H NO.I WS SCHEME |  |  | BILL/01594/2023-2024 | BP-23-24-228 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Quotation deposit for Bonha Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte |  |  | BILL/00830/2024-2025 | BP-24-25-178 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.01 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Different Works related to water supply scheme at Bonha & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE | ORD/000028/2023-2024 | 1216/BHM | 12/04/2023 | 30/04/2025 | TAPAN KUMAR DATTA | 293.99 | 119.81 | 40.75 | 20
Total | [13 empty] | 382.82 | 142.59 | 37.25