## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | DALIMA PIPED WATER SUPPLY SCHEME. | SM/12592 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1438/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 36.19 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Birbhum Division | DALIMA PIPED WATER SUPPLY SCHEME. | SM/12592 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 19/04/2026 | AKASH CONSTRUCTION | 1377.29 | 0 | 0 | 16
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | DALIMA PIPED WATER SUPPLY SCHEME. | SM/12592 | New | Providing Electro-mechanical accessories and others for Dalima PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000867/2023-2024 | 3285/BOL.MD | 29/09/2023 | 01/04/2025 | S.K.ELECTRICALS | 30.88 | 0 | 0 | 70
Total | [13 empty] | 1444.36 | 0 | 0