## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1458/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 10.24 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO .II WS SCHEME |  |  | BILL/01599/2023-2024 | BP-23-24-230 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.16 | 0 | 0 | 0
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO. I WS SCHEME |  |  | BILL/01598/2023-2024 | BP-23-24-229 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.25 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Jogai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000071/2025-2026 | 1593/BHM | 03/06/2025 | 01/09/2025 | QUAZI SIRAJUL ISLAM | 95.37 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Providing Electro-mechanical accessories and others for Jagoi PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000942/2023-2024 | 3303/BOL.MD | 29/09/2023 | 01/04/2025 | SUNRISE ENGINEERING CORPORATION | 28.91 | 0 | 0 | 100
6 | BIRBHUM | Murarai-II | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Different works related to water supply scheme at JOGAI & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE | JE2 | ORD/000064/2023-2024 | 1308/BHM | 19/04/2023 | 01/04/2026 | QUAZI SIRAJUL ISLAM. | 257.76 | 187.3 | 72.66 | 12
Total | [13 empty] | 398.69 | 187.3 | 46.98