## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1569/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 24.53 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | WBSEDCL QUOATION FOR BILASPUR P H NO.II WS SCHEME |  |  | BILL/01597/2023-2024 | BP-23-24-226 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | WBSEDCL QUOTATION FOR BILASPUR PIPED WATER SUPPLY SCHEME.P H NO.I WS SCHEME |  |  | BILL/01596/2023-2024 | BP-23-24-225 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.45 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 01/03/2026 | SUNIL RABI DAS | 1250.5 | 0 | 0 | 60
Total | [13 empty] | 1282.93 | 0 | 0