## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1569/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 24.53 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | WBSEDCL QUOATION FOR BILASPUR P H NO.II WS SCHEME |  |  | BILL/01597/2023-2024 | BP-23-24-226 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | WBSEDCL QUOTATION FOR BILASPUR PIPED WATER SUPPLY SCHEME.P H NO.I WS SCHEME |  |  | BILL/01596/2023-2024 | BP-23-24-225 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.45 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 01/03/2026 | SUNIL RABI DAS | 1250.5 | 113.69 | 9.09 | 60
5 | BIRBHUM | Murarai-II | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Providing Electro-mechanical accessories and others for Bilaspur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000939/2023-2024 | 3300/BOL.MD | 29/09/2023 | 01/04/2025 | SUNIL RABIDAS | 28.71 | 20.52 | 71.49 | 100
6 | BIRBHUM | Murarai-II | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. | SM/12594 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 1379.48 | 134.21 | 9.73