## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1516/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 13.93 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 25/05/2024 | BENGAL ENGINEERING | 1204.06 | 158.31 | 13.15 | 30
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NI.I WS SCHEME |  |  | BILL/01828/2023-2024 | BP-23-24-251 | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | Restoration charges for laying of PHE pipeline from Chainage 5.80 KM (Hiytnagar) to 9.5 KM of Murarai Mitrapur Road under Rampurhat Highway Sub Division of Birbhum Highway Division-_ in the Dist of Birbhum during the year 2023-24 |  |  | BILL/00736/2024-2025 | BP-2024-25-223 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 17.21 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NO.Ii WS SCHEME |  |  | BILL/01829/2023-2024 | BP-23-24-252 | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.21 | 0 | 0 | 0
6 | BIRBHUM | Murarai-II | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. | SM/12595 | New | Providing Electro-mechanical accessories and others for Kashimnagar PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000943/2023-2024 | 3304/BOL.MD | 29/09/2023 | 22/03/2025 | CHAKRABORTY MINING & ENGINERING | 30.42 | 24.79 | 81.47 | 80
Total | [13 empty] | 1271.93 | 183.1 | 14.4