## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Bolpur Mechanical | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | Providing Electro-mechanical accessories and others for Pakuria & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000430/2023-2024 | 2094/Bol.MD | 22/08/2023 | 21/10/2023 | CHAKRABORTY MINING & ENGINERING | 28.81 | 16.67 | 57.86 | 50
2 | BIRBHUM | Sainthia | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 1413/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 17.28 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE,JE1 | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 28/02/2026 | SHREE J.M. CONSTRUCTION | 1236.08 | 193.28 | 15.64 | 54
4 | BIRBHUM | Sainthia | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | Road crossing, repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Pakuria Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | AE | JE1,JE2 | ORD/000041/2025-2026 | 1511/BHM | 23/05/2025 | 21/08/2025 | SHREE J.M. CONSTRUCTION | 18.25 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | New service connection at Pakuria PH-I W/S scheme Block - Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01137/2024-2025 | BP-24-25-311 | 10/01/2025 | 10/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.35 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | PAKURIA PIPED WATER SUPPLY SCHEME. | SM/12596 | New | New service connection at Pakuria PH-II W/S scheme Block - Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01531/2024-2025 | 98/16 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.95 | 0 | 0 | 0
Total | [13 empty] | 1314.72 | 209.95 | 15.97