## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 1368/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 37.96 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | New | New service connection at Samsa PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00219/2024-2025 | BP-24-25-107 | 02/07/2024 | 02/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | New | New service connection at Samsa PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01025/2024-2025 | BP-24-25-279 | 17/12/2024 | 17/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.3 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 23/07/2025 | ASHOK KUMAR GHOSH | 1446.74 | 10.76 | 0.74 | 55
5 | BIRBHUM | Sainthia | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. | SM/12597 | New | Providing Electro-mechanical accessories and others for Samsa & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000437/2023-2024 | 2096/Bol.MD | 22/08/2023 | 20/02/2026 | M/S SWAPAN BANERJEE | 28.57 | 21.5 | 75.27 | 80
Total | [13 empty] | 1519.58 | 32.26 | 2.12