## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 1414/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 18.66 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | New | New service connection at Purba Siur PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02243/2023-2024 | BP-2023-24-318 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.77 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | New | New service connection at Purba Siur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02242/2023-2024 | BP-2023-24-317 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 28/09/2025 | B RAI CONSTRUCTION COMPANY | 1402.44 | 35.05 | 2.5 | 45
5 | BIRBHUM | Sainthia | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. | SM/12598 | New | Providing Electro-mechanical accessories and others for Purba Siur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000411/2023-2024 | 2084/Bol.MD | 22/08/2023 | 01/11/2025 | STANDARD ELECTRICALS | 29.66 | 19.52 | 65.79 | 80
Total | [13 empty] | 1457.48 | 54.57 | 3.74