## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1452/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 8.28 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Providing Electro-mechanical accessories and others for Kushipur PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000911/2023-2024 | 3540/BOL.MD | 30/11/2023 | 29/01/2024 | S.G.TECHNICAL SERVICES | 27.3 | 18.8 | 68.88 | 40
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | QUOTATION FOR KUHSIPUR PH 2 NALHATI-I BLOCK |  |  | BILL/00003/2024-2025 | BP-24-25-04 | 09/04/2024 | 09/04/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | WBSEDCL QUOTATION FOR KUSHIPUR W/S SCHEME PH-2 (NALHATI-1) |  |  | BILL/02465/2023-2024 |  | 27/03/2024 | 27/03/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
6 | BIRBHUM | Nalhati-I | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Jack pushing & Augur boring along with extension of pipeline (DI & HDPE), restoration of Roads & all allied works for Kushipur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000627/2024-2025 | 658/BHM | 07/03/2025 | 06/05/2025 | SK ALIM | 81.8 | 0 | 0 | 60
7 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Quotation for new service connection at Kushipur PWSS P/H- I (Mouza- Madhura) at Block- Nalhati-I |  |  | BILL/01126/2024-2025 | BP-24-25-295 | 10/01/2025 | 10/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.5 | 0 | 0 | 0
8 | BIRBHUM | Nalhati-I | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. | SM/12599 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 01/10/2025 | SK ALIM | 1229.19 | 245.36 | 19.96 | 25
Total | [13 empty] | 1410.97 | 264.16 | 18.72