## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) | SM/12637 | Retrofitting | Balance work for laying of pipe line including FHTC within the command area of Aligarh (Phase III) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000127/2023-2024 | 2272/BHM | 13/07/2023 | 27/08/2023 | PARTHA PRATIM ACHARYYA | 32.89 | 19.93 | 60.58 | 40
Total | [13 empty] | 32.89 | 19.93 | 60.58