## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Central Drilling | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | Providing drilling crew and other allied works for construction of Tube Well(250mm X 200mmx 150mtrs Depth) by utilising Departmental Machineries for Neturi W/S scheme (TW-I), Sainthia Block under Birbhum District , CDD,PHE DTE. | Driller In Charge | Junior Engineer | ORD/000277/2022-2023 | 1134/CDD | 04/11/2022 | 04/12/2022 | C.M. ENTERPRISE | 10.99 | 8.77 | 79.81 | 0
2 | BIRBHUM | Sainthia | Central Drilling | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NETURI W/S SCH (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000343/2022-2023 | 1135/CDD | 04/11/2022 | 04/12/2022 | C.M. ENTERPRISE | 10.99 | 8.31 | 75.57 | 0
3 | BIRBHUM | Sainthia | Birbhum Division | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1418/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 11.04 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | WBSEDCL QUOTATION FOR NETURI WS SCHEME |  |  | BILL/00700/2023-2024 | BP-2023-2024-60 | 02/08/2023 | 02/08/2023 | WBSEDCL | 4.86 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | WBSEDCL QUOTATION FOR NETURI WS SCHEME P.H NO.I |  |  | BILL/00704/2023-2024 | BP-2023-2024-59 | 02/08/2023 | 02/08/2023 | WBSEDCL | 4.95 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | Providing Electro-mechanical accessories and others for Neturi & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000785/2022-2023 | 322/BOL.M.D | 27/03/2023 | 01/02/2025 | ABHISEK ENGTNEERING CONCERN | 28.92 | 27.79 | 96.1 | 35
7 | BIRBHUM | Sainthia | Birbhum Division | NETURI PIPED WATER SUPPLY SCHEME. | SM/12656 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 28/02/2026 | SHREE J.M. CONSTRUCTION | 1236.08 | 389.79 | 31.53 | 54
Total | [13 empty] | 1307.82 | 434.65 | 33.24